## RAG Dashboard
Metric | Target | Actual | RAG | Trend | S1 | S2 | S3 | S4 | S5 | S6
Execution Progress | 90% | 75% | AMBER | +8% | 10% | 25% | 40% | 55% | 67% | 75%
Pass Rate | 95% | 90% | AMBER | +1% | 96% | 93% | 88% | 86% | 89% | 90%
Defect Discovery Rate | <5/day | 2.3/day | GREEN | -0.7 | 0.8 | 1.5 | 2.8 | 3.2 | 2.5 | 1.8
Blocked Rate | <5% | 3% | GREEN | -1% | 5% | 4% | 6% | 5% | 4% | 3%
Open Critical Defects | 0 | 8 | RED | +2 | 0 | 1 | 3 | 5 | 6 | 8
Requirements Coverage | 95% | 84% | AMBER | +10% | 15% | 32% | 48% | 62% | 74% | 84%
Risk Coverage (Class A) | 90% | 92% | GREEN | +5% | 20% | 40% | 60% | 78% | 87% | 92%
Automation Rate | 60% | 42% | AMBER | +2% | 12% | 22% | 30% | 36% | 40% | 42%
Environment Availability | 95% | 97% | GREEN | 0% | 92% | 94% | 88% | 95% | 96% | 97%
Schedule Adherence | 90% | 82% | AMBER | +3% | 95% | 90% | 78% | 75% | 79% | 82%

## Execution by Level
Test Level | Planned | Executed | Passed | Failed | Blocked | Exec% | Pass%
Unit | 1200 | 1200 | 1152 | 36 | 12 | 100% | 96%
Component | 800 | 760 | 700 | 45 | 15 | 95% | 92%
Integration | 950 | 820 | 722 | 74 | 24 | 86% | 88%
System | 1500 | 910 | 773 | 96 | 41 | 61% | 85%
SIT | 600 | 300 | 252 | 27 | 21 | 50% | 84%
UAT | 400 | 100 | 82 | 8 | 10 | 25% | 82%
TOTAL

## Execution by Type
Test Type | Planned | Executed | Passed | Failed | Blocked | Exec% | Pass%
Functional | 2800 | 2240 | 2061 | 134 | 45
Performance | 650 | 455 | 387 | 50 | 18
Security | 500 | 400 | 368 | 24 | 8
Regression | 1000 | 750 | 698 | 37 | 15
Smoke | 500 | 245 | 167 | 41 | 37
TOTAL

## Execution by Priority
Priority | Planned | Executed | Passed | Failed | Blocked | Exec% | Pass%
Critical | 820 | 738 | 672 | 48 | 18
High | 1630 | 1304 | 1187 | 82 | 35
Medium | 2000 | 1400 | 1274 | 98 | 28
Low | 1000 | 648 | 548 | 58 | 42
TOTAL

## Defect Summary
Severity | New | Open | In Progress | Resolved | Closed | Reopened | Total
Critical | 1 | 3 | 2 | 1 | 1 | 0
Major | 2 | 4 | 3 | 3 | 2 | 1
Minor | 1 | 3 | 2 | 5 | 6 | 1
Trivial | 0 | 2 | 0 | 1 | 3 | 0
TOTAL

## Feature Defects
Rank | Feature | TCs Failed | Total Defects | Critical | Major | Minor | Defect Density
1 | Payment Processing | 42 | 8 | 3 | 4 | 1 | 0.38
2 | Checkout Process | 38 | 6 | 2 | 3 | 1 | 0.16
3 | Order Management | 28 | 5 | 1 | 3 | 1 | 0.18
4 | Security/Auth | 24 | 5 | 1 | 2 | 2 | 0.21
5 | Shopping Cart | 22 | 4 | 1 | 2 | 1 | 0.18
6 | Coupon/Discount | 18 | 4 | 0 | 2 | 2 | 0.22
7 | Tax Calculation | 16 | 3 | 0 | 1 | 2 | 0.19
8 | Shipping & Delivery | 14 | 3 | 0 | 1 | 2 | 0.21
9 | Inventory Management | 12 | 2 | 0 | 1 | 1 | 0.17
10 | Search & Navigation | 10 | 2 | 0 | 0 | 2 | 0.20

## Quality Assessment
Quality Characteristic | Status | Score | Evidence | Gaps | Recommendation
Functional Suitability | AMBER | 84 | 286 failures under investigation | Partial feature coverage | Complete remaining features
Performance Efficiency | AMBER | N/A | Page load: 2100ms vs 2000ms target | API response 10% below target | Optimize DB queries
Compatibility | GREEN | 100 | Chrome, Firefox, Edge, Safari, iOS, Android tested | None | Maintain current browser matrix
Usability | AMBER | N/A | UAT 25% complete, 3 issues logged | Cart and checkout UX incomplete | Complete UAT with user feedback
Reliability | AMBER | N/A | MTBF: 72hrs vs 100hrs target | Recovery procedure needs testing | Increase test coverage for edge cases
Security | AMBER | N/A | OWASP 9/10 passed, PCI-DSS 10/12 | 1 XSS vulnerability pending | Complete XSS remediation and retesting
Maintainability | GREEN | N/A | 78% code coverage, modularity 8.2/10 | None | Maintain static analysis discipline
Portability | GREEN | 100 | Docker verified, migration scripts tested | None | Validate cross-platform deployment

## Exit Criteria
# | Exit Criterion | Target | Actual | Status | Evidence | Action Required
1 | Functional completeness | 100% | 100% | PASS | All core features implemented | None
2 | Code coverage >= 75% | 75% | 78% | PASS | Code coverage report verified | None
3 | Documentation complete | 100% | 100% | PASS | User and admin guides published | None
4 | Unit test automation | 80% | 96% | PASS | Unit test suite executed daily | None
5 | Security scan passed | Pass | Pass | PASS | SAST scan: 0 critical issues | None
6 | Critical defects resolved | 0 | 8 | FAIL | Escalated to dev team | Resolve by Sprint 7
7 | Production environment ready | Ready | Ready | PASS | Environment provisioned and tested | None
8 | Database migration validated | Verified | Verified | PASS | Migration scripts executed successfully | None
9 | Performance baseline established | Baseline | Baseline | PASS | Load test results documented | None
10 | Disaster recovery tested | Tested | Tested | PASS | DR procedures executed | None
11 | Compliance audit passed | Passed | Passed | PASS | PCI-DSS compliance verified | None
12 | Third-party integration tested | 100% | 100% | PASS | Payment gateway, shipping API verified | None
13 | Mobile app regression passed | 100% | 100% | PASS | iOS and Android test suites completed | None
14 | API load testing passed | 500 TPS | 450 TPS | PARTIAL | Load test at 90% target | Optimization needed
15 | Inventory sync verified | 100% | 86% | PARTIAL | Integration tests 86% complete | Complete race condition testing
16 | Customer data protection validated | 100% | 100% | PASS | GDPR compliance verified | None
17 | Browser compatibility | 4 browsers | 4 browsers | PASS | Chrome, Firefox, Edge, Safari tested | None
18 | Accessibility compliance | WCAG 2.1 AA | WCAG 2.1 AA | PASS | Accessibility audit passed | None
19 | Email notification testing | 100% | 100% | PASS | All email templates verified | None
20 | Search functionality | 100% | 100% | PASS | Search tests executed | None
21 | Reporting accuracy | 100% | 95% | PARTIAL | Report data validation 95% complete | Validate remaining edge cases
22 | Coupon/Discount logic | 100% | 100% | PASS | Comprehensive test coverage | None
23 | Pass rate >= 95% | 95% | 90% | FAIL | Currently at 90% pass rate | Complete remaining test cases
24 | Requirements coverage >= 90% | 90% | 84% | AMBER | Coverage at 84% | Map remaining requirements
25 | UAT completion >= 80% | 80% | 25% | FAIL | UAT only 25% complete | Accelerate UAT execution
26 | Performance within target | Within 5% | Within 5% | PARTIAL | Page load time 5% above target | Continue optimization
27 | Security vulnerabilities resolved | 0 | 1 | FAIL | XSS vulnerability pending | Patch and validate by Sprint 7
28 | Defect resolution >= 80% | 80% | 85% | PASS | Defect removal efficiency 87% | None
29 | Risk mitigation >= 80% | 80% | 79.2% | PARTIAL | Overall risk mitigation 79.2% | Focus on Class C risks
30 | Smoke tests 100% pass | 100% | 68% | PARTIAL | Smoke test pass rate 68% | Debug failing smoke tests
31 | Regression test execution | 100% | 80% | PARTIAL | Regression tests 80% executed | Complete remaining regression tests
32 | Release notes prepared | Complete | Complete | PASS | Release notes published | None
33 | Known issues documented | Complete | Complete | PASS | Known issues list finalized | None
34 | Go/no-go approval | Approved | Conditional | PARTIAL | Conditional GO approved | Resolve critical blockers

## Release Advice
RELEASE RECOMMENDATION: CONDITIONAL GO
Recommendation | CONDITIONAL GO
Confidence Level | 78%
Current Sprint | Sprint 6 of 8
Projected Release | End of Sprint 8 (2 weeks)
Key Blocker | 8 critical defects require resolution
CONDITIONS FOR RELEASE
Condition # | Condition | Owner | Effort | Target Date | Status
1 | Resolve all 8 critical defects | Dev Team - 3 engineers | 40 hours | Sprint 7 (1 week) | IN PROGRESS
2 | Patch XSS vulnerability | Security Team | 8 hours | Sprint 7 (3 days) | IN PROGRESS
3 | Complete UAT for Payment/Checkout (80% min) | QA + Business Team | 80 hours | Sprint 7-8 (2 weeks) | NOT STARTED
4 | Performance tuning for throughput target (500 TPS) | Performance Team | 32 hours | Sprint 8 (1 week) | IN PROGRESS

## Risk Mitigation
Risk ID | Risk Description | Class | Mitigation % | Status | Test Evidence | Residual Risk
RSK-001 | Payment data breach | A | 92 | Mitigated | PCI-DSS tests passed 10/12, pen test completed, encryption verified | Low
RSK-002 | Order processing failure | A | 75 | Partially Mitigated | Transaction tests 85% complete, rollback verified, edge cases pending | Medium
RSK-003 | Authentication bypass | A | 88 | Mitigated | OWASP auth tests passed, session management verified, 1 XSS pending | Low
RSK-004 | Data loss during migration | A | 95 | Mitigated | Migration scripts tested, rollback verified, backup procedures tested | Low
RSK-005 | Performance degradation under load | A | 70 | Partially Mitigated | Load tests at 80% target, stress test revealed bottleneck in cart service | Medium
RSK-006 | Shopping cart calculation errors | A | 90 | Mitigated | BVA + EP comprehensive, tax calc verified, coupon edge cases covered | Low
RSK-007 | Checkout process abandonment | A | 65 | Partially Mitigated | UX testing incomplete, 3 usability issues open | Medium
RSK-008 | SQL injection vulnerability | A | 98 | Mitigated | All input fields parameterized, SQL injection tests passed, WAF configured | Low
RSK-009 | Inventory sync failures | A | 72 | Partially Mitigated | Integration tests 86% complete, race condition under investigation | Medium
RSK-010 | GDPR compliance failure | A | 85 | Mitigated | Data export/deletion tested, consent management verified, cookie compliance pending | Low
RSK-011 | Multi-currency calculation errors | A | 80 | Mitigated | Core calculations verified, edge cases for rounding pending | Low
RSK-012 | Email notification failures | B | 75 | Mitigated | Email template tests passed | Low
RSK-013 | Search result relevance | B | 70 | Mitigated | Search tests 70% complete | Medium
RSK-014 | Shipping rate calculation | B | 80 | Mitigated | Shipping module tests passed | Low
RSK-015 | Tax jurisdiction handling | B | 78 | Partially Mitigated | Tax calc 78% tested | Medium
RSK-016 | Admin dashboard authorization | B | 82 | Mitigated | Authorization tests passed | Low
RSK-017 | Plugin compatibility | B | 65 | Partially Mitigated | 65% of plugins tested | Medium
RSK-026 | Browser-specific rendering | C | 60 | Partially Mitigated | 4 browsers tested | Low
RSK-027 | Print stylesheet formatting | C | 45 | Partially Mitigated | Print tests 45% done | Medium

## Sprint Trends
Metric | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Trend
Velocity (TC/day) | 45 | 78 | 105 | 128 | 135 | 142 | UP
Discovery Rate (/day) | 0.8 | 1.5 | 2.8 | 3.2 | 2.5 | 1.8 | DOWN
Resolution Rate (/day) | 0.3 | 0.8 | 1.5 | 2.2 | 2.8 | 3.1 | UP
Pass Rate (%) | 96 | 93 | 88 | 86 | 89 | 90 | RECOVERING
Coverage (%) | 15 | 32 | 48 | 62 | 74 | 84 | UP
Automation (%) | 12 | 22 | 30 | 36 | 40 | 42 | UP

## Root Cause Pareto
Root Cause | Count | Percentage | Cumulative %
Input Validation | 13 | 28% | 28%
Business Logic | 10 | 22% | 50%
Integration/API | 7 | 15% | 65%
UI/UX | 6 | 13% | 78%
Performance | 4 | 9% | 87%
Security | 3 | 7% | 93%
Configuration | 2 | 4% | 98%
Data | 1 | 2% | 100%

## Lessons Learned
Area | What Went Well | What Could Improve | Action | Owner | Priority
Test Planning | Early risk analysis saved 15% rework | Estimation 30% under actual | Use historical data + PERT | QA Lead | High
Test Design | BVA/EP found 12 critical defects early | Classification tree underused | CTM training | Test Lead | Medium
Test Execution | Automation saved 320 hours | Manual regression still 58% | Increase automation to 60% | Auto Engineer | High
Environment | Docker standardization improved consistency | Sprint 3 outage cost 5 days | Add environment monitoring | DevOps | Critical
Defect Management | Triage meetings effective (daily) | Defect age > 14 days for 5 defects | Escalation policy enforcement | QA Manager | High
Stakeholder Mgmt | Weekly demos increased confidence | UAT started late (Sprint 6) | Earlier UAT engagement | PO | Medium
Security Testing | OWASP coverage 9/10 | XSS found late (Sprint 5) | Shift-left security testing | Sec Lead | High
Performance | Load testing found cart bottleneck | Stress testing started Sprint 5 | Performance testing from Sprint 2 | Perf Engineer | Medium