## Agile Test Plan
Task ID | Test Task | Story Points | Assigned To | Status | Priority
T001 | Setup test environment | 3 | DevOps | Done | P0
T002 | Create product catalog test suite | 8 | Alice | In Progress | P0
T003 | Create checkout flow tests | 13 | Bob | In Progress | P0
T004 | Create payment gateway tests | 5 | Carol | Backlog | P0
T005 | Create order management tests | 8 | David | Backlog | P1
T006 | Create shipping integration tests | 5 | Eve | Backlog | P1
T007 | Create tax calculation tests | 3 | Frank | Backlog | P1
T008 | Create promotion tests | 5 | Grace | Backlog | P1
T009 | Create customer account tests | 5 | Henry | Backlog | P2
T010 | Create search & navigation tests | 8 | Iris | Backlog | P1
T011 | Create inventory tests | 5 | Jack | Backlog | P1
T012 | Create multi-language tests | 3 | Karen | Backlog | P2
T013 | Create multi-currency tests | 3 | Leo | Backlog | P2
T014 | Create mobile responsive tests | 5 | Mia | Backlog | P1
T015 | Create API tests | 8 | Noah | Backlog | P1
T016 | Create security tests | 13 | Olivia | Backlog | P0
T017 | Create performance tests | 8 | Paul | Backlog | P1
T018 | Create accessibility tests | 5 | Quinn | Backlog | P2
T019 | Create data integrity tests | 5 | Rachel | Backlog | P1
T020 | Create reporting tests | 3 | Sam | Backlog | P2
T021 | Create admin dashboard tests | 5 | Tina | Backlog | P2
T022 | Create email notification tests | 3 | Uma | Backlog | P2
T023 | Create wishlist tests | 3 | Victor | Backlog | P3
T024 | Create review/rating tests | 3 | Wendy | Backlog | P3
T025 | Create plugin/extension tests | 5 | Xavier | Backlog | P3
TOTALS