## Risk Matrix
Risk ID | Risk Description | Feature Area | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy
R001 | Payment gateway integration failure | Payment Processing | 2 | 5 | 10 | Fallback payment method, redundancy
R002 | Database performance degradation | Performance | 3 | 4 | 12 | Indexing, caching, monitoring
R003 | Security vulnerability in authentication | Security | 2 | 5 | 10 | Code review, penetration testing
R004 | Inventory race condition | Inventory Management | 3 | 4 | 12 | Transaction locks, version control
R005 | Email notification failures | Email Notifications | 3 | 2 | 6 | Queue retry mechanism, monitoring
R006 | Search performance on large catalogs | Search & Navigation | 4 | 3 | 12 | Elasticsearch, caching, pagination
R007 | Multi-currency rounding errors | Tax Calculation | 2 | 3 | 6 | Decimal type validation, testing
R008 | Shipping integration API downtime | Shipping & Delivery | 3 | 4 | 12 | Multiple carrier support, fallback
R009 | Admin dashboard slow reporting | Admin Dashboard | 3 | 2 | 6 | Query optimization, materialized views
R010 | Coupon/discount edge cases | Coupon/Discount Engine | 2 | 3 | 6 | Comprehensive test coverage
R011 | Mobile responsive layout failures | UI/UX | 2 | 2 | 4 | CSS testing, responsive framework
R012 | API rate limiting bypassed | API Integration | 2 | 4 | 8 | Stricter validation, monitoring
R013 | Data migration data loss | Data Integrity | 1 | 5 | 5 | Validation, reconciliation, backup
R014 | Third-party plugin compatibility | Plugin Architecture | 3 | 3 | 9 | Sandbox testing, version management
R015 | SSL certificate expiration | Security | 1 | 4 | 4 | Automated renewal, monitoring
R016 | Database replication lag | Order Management | 2 | 3 | 6 | Synchronization monitoring
R017 | Search index out of sync | Search & Navigation | 2 | 3 | 6 | Real-time indexing
R018 | Wishlist data corruption | Wishlist | 1 | 2 | 2 | Backup, validation
R019 | Review moderation backlog | Customer Reviews | 2 | 2 | 4 | Automated filtering, staffing
R020 | Multi-language translation errors | Multi-language | 2 | 2 | 4 | Professional translation review
R021 | Concurrent checkout conflicts | Checkout Process | 2 | 4 | 8 | Optimistic locking
R022 | Cart abandonment due to errors | Shopping Cart | 3 | 3 | 9 | Error handling, recovery
R023 | Inventory sync delay | Inventory Management | 3 | 2 | 6 | Real-time sync, monitoring
R024 | Report generation timeout | Reporting/Analytics | 2 | 2 | 4 | Async processing, caching
R025 | Customer data privacy breach | Customer Accounts | 1 | 5 | 5 | Encryption, access controls, audit
R026 | Product image loading failures | Product Catalog Management | 2 | 2 | 4 | CDN, fallback images
R027 | Tax service API unavailable | Tax Calculation | 2 | 4 | 8 | Fallback rates, caching
R028 | Campaign discount calculation error | Coupon/Discount Engine | 2 | 3 | 6 | Comprehensive validation
R029 | Negative customer reviews flooding | Customer Reviews | 2 | 2 | 4 | Moderation queue, automated filters
R030 | SEO duplicate content issues | SEO Optimization | 1 | 2 | 2 | Canonical tags, robots.txt
R031 | Performance degradation peak hours | Performance/Caching | 3 | 4 | 12 | Load testing, auto-scaling
R032 | API documentation outdated | API Integration | 2 | 2 | 4 | Automated docs from code