## Metrics Dashboard
KPI | Target | Actual | Status | Trend | Notes
Test Pass Rate | 95% | 92% | At Risk | Improving | 4 critical bugs found this sprint
Code Coverage | 85% | 78% | Below Target | Stable | Unit tests need improvement
Defect Density | 0.5/KLOC | 0.7/KLOC | At Risk | Stable | More defects than baseline
Test Execution Rate | 90% | 88% | On Track | Stable | One test suite delayed
Regression Coverage | 80% | 82% | Exceeds Target | Improving | Good baseline regression suite
Critical Bugs Found | 0 | 2 | At Risk | Increasing | Payment & security issues
Defect Escape Rate | 5% | 6% | At Risk | Increasing | Production defect reports up
Test Cycle Time | 2 weeks | 2.1 weeks | On Track | Stable | Additional testing added
Automation Rate | 60% | 55% | Below Target | Declining | Need more automation scripts
Requirement Traceability | 100% | 98% | At Risk | Declining | 2 requirements not traced
Effort Estimation Accuracy | 85% | 80% | On Track | Stable | 1-2% variance typical
Risk Mitigation Coverage | 90% | 88% | On Track | Stable | Most risks mitigated
Team Productivity | 40 SP/sprint | 38 SP/sprint | On Track | Stable | Normal variation
Test Environment Uptime | 99% | 98.5% | On Track | Stable | One 2-hour outage
Customer Satisfaction | 4.5/5 | 4.2/5 | Below Target | Declining | Address quality issues