## Summary
Metric | Value | Target | Status
Total Test Cases | 356 | 356
Test Cases Passed | 312 | 340
Test Cases Failed | 32 | 16
Pass Rate % |  | 95
Defects Found | 32 | 35
Defects Resolved | 28 | 30
Coverage % | 98 | 95
Test Execution Time (days) | 21 | 25

## By Feature
Feature | Test Cases | Passed | Failed | Pass % | Coverage %
Feature_1 | 15 | 14 | 1 |  | 96
Feature_2 | 16 | 14 | 2 |  | 97
Feature_3 | 17 | 17 | 0 |  | 98
Feature_4 | 14 | 13 | 1 |  | 99
Feature_5 | 15 | 13 | 2 |  | 95
Feature_6 | 16 | 16 | 0 |  | 96
Feature_7 | 17 | 16 | 1 |  | 97
Feature_8 | 14 | 12 | 2 |  | 98
Feature_9 | 15 | 15 | 0 |  | 99
Feature_10 | 16 | 15 | 1 |  | 95
Feature_11 | 17 | 15 | 2 |  | 96
Feature_12 | 14 | 14 | 0 |  | 97
Feature_13 | 15 | 14 | 1 |  | 98
Feature_14 | 16 | 14 | 2 |  | 99
Feature_15 | 17 | 17 | 0 |  | 95
Feature_16 | 14 | 13 | 1 |  | 96
Feature_17 | 15 | 13 | 2 |  | 97
Feature_18 | 16 | 16 | 0 |  | 98
Feature_19 | 17 | 16 | 1 |  | 99
Feature_20 | 14 | 12 | 2 |  | 95
Feature_21 | 15 | 15 | 0 |  | 96
Feature_22 | 16 | 15 | 1 |  | 97
Feature_23 | 17 | 15 | 2 |  | 98
Feature_24 | 14 | 14 | 0 |  | 99
Feature_25 | 15 | 14 | 1 |  | 95

## By Priority
Priority | Count | Passed | Failed | Pass %
P0 | 79 | 77 | 2
P1 | 69 | 65 | 4
P2 | 59 | 53 | 6
P3 | 49 | 41 | 8

## Defects
Defect ID | Severity | Status | Component | Found By
DEF001 | Major | In Progress | Shopping Cart | Tester2
DEF002 | Minor | Fixed | Checkout | Tester3
DEF003 | Trivial | Closed | Payment | Tester1
DEF004 | Critical | Open | User Management | Tester2
DEF005 | Major | In Progress | Orders | Tester3
DEF006 | Minor | Fixed | Customers | Tester1
DEF007 | Trivial | Closed | Inventory | Tester2
DEF008 | Critical | Open | Search | Tester3
DEF009 | Major | In Progress | Reviews | Tester1
DEF010 | Minor | Fixed | Product Catalog | Tester2
DEF011 | Trivial | Closed | Shopping Cart | Tester3
DEF012 | Critical | Open | Checkout | Tester1
DEF013 | Major | In Progress | Payment | Tester2
DEF014 | Minor | Fixed | User Management | Tester3
DEF015 | Trivial | Closed | Orders | Tester1
DEF016 | Critical | Open | Customers | Tester2
DEF017 | Major | In Progress | Inventory | Tester3
DEF018 | Minor | Fixed | Search | Tester1
DEF019 | Trivial | Closed | Reviews | Tester2
DEF020 | Critical | Open | Product Catalog | Tester3
DEF021 | Major | In Progress | Shopping Cart | Tester1
DEF022 | Minor | Fixed | Checkout | Tester2
DEF023 | Trivial | Closed | Payment | Tester3
DEF024 | Critical | Open | User Management | Tester1
DEF025 | Major | In Progress | Orders | Tester2
DEF026 | Minor | Fixed | Customers | Tester3
DEF027 | Trivial | Closed | Inventory | Tester1
DEF028 | Critical | Open | Search | Tester2
DEF029 | Major | In Progress | Reviews | Tester3
DEF030 | Minor | Fixed | Product Catalog | Tester1
DEF031 | Trivial | Closed | Shopping Cart | Tester2
DEF032 | Critical | Open | Checkout | Tester3