## 3-Point Estimation
Feature | Optimistic (O) | Expected (E) | Pessimistic (P) | PERT Estimate | Risk Factor
User Registration | 3 | 5 | 8
User Login | 2 | 3 | 5
Product Browsing | 4 | 6 | 10
Search Functionality | 5 | 8 | 12
Product Details | 3 | 5 | 8
Shopping Cart | 4 | 7 | 11
Wishlist | 2 | 4 | 7
Checkout Flow | 6 | 10 | 15
Payment Processing | 8 | 12 | 18
Order Management | 5 | 8 | 12
Order History | 3 | 5 | 8
Reviews & Ratings | 4 | 6 | 9
Inventory Management | 5 | 8 | 12
Discount Management | 4 | 7 | 11
Shipping | 6 | 9 | 14
Returns Management | 5 | 8 | 12
Notifications | 4 | 6 | 9
Customer Support | 5 | 8 | 12
Admin Dashboard | 8 | 12 | 18
Reports | 6 | 10 | 15
Analytics | 7 | 11 | 16
Security Testing | 6 | 10 | 15
Performance Testing | 5 | 9 | 14
API Testing | 5 | 8 | 12
Mobile Responsive | 6 | 10 | 15