MASTER TEST PLAN

nopCommerce E-Commerce Platform

Document ID: MTP-NOPC-001

Version: 1.0

Date: 2026-04-06

Standard Reference: ISO 29119-3

Classification: CONFIDENTIAL

TABLE OF CONTENTS

1. Introduction

2. Test Strategy

3. Test Schedule

4. Test Levels

5. Resource Plan

6. Non-Functional Testing

7. End-to-End Testing

8. Environment Plan

9. Test Data Strategy

10. Risk Management

11. Metrics and Reporting

12. Entry and Exit Criteria

Appendix A: Budget Breakdown

Appendix B: Glossary

1. INTRODUCTION

1.1 Purpose

This Master Test Plan (MTP) defines the comprehensive testing strategy, approach, resource allocation, and schedule for the nopCommerce e-commerce platform. The plan adheres to ISO 29119-3 standards and establishes the framework for all testing activities across the 25 features and 153 functional requirements.

1.2 Scope

The MTP covers all functional requirements (REQ001-REQ153), non-functional requirements (103 NFRs), and quality assurance activities for the nopCommerce platform. Testing includes UI/UX, accessibility (WCAG 2.1 AA), GDPR compliance, security (OWASP Top 10), performance, and integration testing.

1.3 References

- ISO/IEC/IEEE 29119-3:2013 - Software and systems engineering - Software testing - Part 3: Test documentation

- OWASP Top 10 - Web Application Security Risks

- WCAG 2.1 - Web Content Accessibility Guidelines

- GDPR - General Data Protection Regulation Compliance

- IEEE Std 830-1998 - Software Requirements Specification

2. TEST STRATEGY

2.1 Overall Approach

The testing strategy follows a Risk-Based Testing approach with balanced coverage across functional, non-functional, and quality dimensions. Testing is organized into 6 levels (unit, component, integration, system, system integration, and acceptance) with specific techniques aligned to each feature's risk profile.

2.2 Test Technique Selections

Test techniques are selected based on feature complexity, risk, and requirement characteristics:

- Equivalence Partitioning: Data validation and boundary conditions

- Boundary Value Analysis: Limits and thresholds

- Decision Table Testing: Complex business rules and combinations

- State Transition Testing: Stateful processes (order lifecycle, payments)

- Use Case Flow Testing: End-to-end user journeys

- Combinatorial Testing: Multi-parameter interactions

- Error Guessing: Exception and error handling

- Security Testing: OWASP Top 10, authentication, encryption

2.3 Risk-Based Allocation

Testing effort is allocated based on risk factors: criticality of features (payment processing, user management), complexity, code coverage targets, and historical defect density. Critical features receive 40% of test effort, major features 35%, and minor features 25%.

3. TEST SCHEDULE

3.1 Testing Phases and Milestones

The testing program is structured in phases with defined entry/exit criteria:

| Phase | Duration | Start Date | End Date | Key Milestones |
| --- | --- | --- | --- | --- |
| Unit Testing | 4 weeks | Week 1 | Week 4 | Code coverage >85% |
| Component Testing | 3 weeks | Week 5 | Week 7 | Component test reports |
| Integration Testing | 4 weeks | Week 8 | Week 11 | Integration matrix signed off |
| System Testing | 5 weeks | Week 12 | Week 16 | System test complete |
| E2E & UAT | 3 weeks | Week 17 | Week 19 | UAT sign-off |
| Go-Live Prep | 2 weeks | Week 20 | Week 21 | Production release ready |

3.2 Dependencies and Critical Path

- Unit testing must be 80% complete before component testing begins

- All critical defects from lower levels must be resolved before system testing

- Performance testing to run in parallel with system testing in isolated environment

- Security testing to run throughout all phases with focused effort in weeks 12-16

4. TEST LEVELS

Testing is organized into 6 levels, each with specific objectives, entry/exit criteria, and success metrics.

4.1 Level 1: Unit Testing

Objectives:

- Verify individual units/methods function correctly in isolation

- Achieve minimum 85% code coverage with emphasis on critical paths

- Validate error handling and exception scenarios

Entry Criteria:

- Code unit review completed and approved

- Unit test framework configured and integrated with CI/CD

- Development environment stable

Techniques:

- White-box testing with boundary value analysis

- Path testing for critical algorithms

- Equivalence partitioning for input validation

Coverage Targets:

| Metric | Target | Payment Module | Security Module | Core Logic |
| --- | --- | --- | --- | --- |
| Statement Coverage | 85% | 95% | 95% | 85% |
| Branch Coverage | 75% | 90% | 90% | 75% |
| Path Coverage | 60% | 80% | 80% | 60% |

Exit Criteria:

- Minimum 85% code coverage achieved

- All high-priority unit test failures resolved

- Unit test report generated and reviewed

4.2 Level 2: Component Testing

Objectives:

- Test individual software components in isolation

- Verify component interfaces and interactions

- Validate data flow between components

Entry Criteria:

- Unit testing 80% complete with passing results

- Component specification approved

- Test environment prepared with required dependencies

Techniques:

- Black-box testing with boundary value analysis

- Interface testing (API contracts, data structures)

- State-based testing for stateful components

Component Coverage:

| Component | Type | Test Cases | Pass Rate Target | Status |
| --- | --- | --- | --- | --- |
| Product Catalog | Core | 45 | 95% | Planned |
| Shopping Cart | Core | 52 | 95% | Planned |
| Payment Gateway | Critical | 38 | 98% | Planned |
| User Management | Core | 41 | 96% | Planned |
| Order Processing | Core | 44 | 96% | Planned |

Exit Criteria:

- All component test cases executed

- 95% pass rate achieved for standard components, 98% for critical

- Component integration issues documented

4.3 Level 3: Integration Testing

Objectives:

- Verify interactions between integrated components

- Validate end-to-end data flows across system

- Test third-party integrations (payment gateways, shipping)

Entry Criteria:

- Component testing complete with >95% pass rate

- Integration test plan approved

- Integration test environment fully prepared

Techniques:

- Top-down integration strategy for critical paths

- Bottom-up integration for foundational components

- Smoke testing of integrated flows

- Error propagation testing

Integration Scope:

| Integration Area | Components Involved | Test Cases | Priority | External Systems |
| --- | --- | --- | --- | --- |
| Payment Flow | Cart -> Checkout -> Payment | 28 | Critical | Gateway APIs |
| Order Management | Orders -> Inventory -> Shipping | 24 | Critical | Shipping APIs |
| User Data | Registration -> Profile -> Orders | 18 | High | Email Service |
| Search & Catalog | Search -> Filters -> Products | 16 | High | Search Engine |

Exit Criteria:

- All integration test cases executed

- Critical integration paths validated

- Third-party integrations verified functional

4.4 Level 4: System Testing

Objectives:

- Verify complete system against all functional requirements

- Validate system performance and reliability

- Test all 25 features in realistic scenarios

Entry Criteria:

- Integration testing complete

- System test environment stable with production-like configuration

- System test cases documented and reviewed

Techniques:

- End-to-end functional testing for all features

- Use case flow testing matching real user journeys

- Negative testing for error handling

- Regression testing of impacted areas

Feature Coverage:

| Feature ID | Feature Name | Requirements | Test Cases | Est. Coverage |
| --- | --- | --- | --- | --- |
| F01 | Product Catalog | REQ001-REQ015 | 45 | 100% |
| F02 | Shopping Cart | REQ016-REQ030 | 42 | 100% |
| F03 | Checkout | REQ031-REQ040 | 35 | 100% |
| F04 | Payments | REQ041-REQ050 | 48 | 100% |
| F05 | User Mgmt | REQ051-REQ065 | 38 | 100% |

Exit Criteria:

- 100% of 153 functional requirements traced to test cases

- 90% pass rate on first execution

- All critical defects resolved

4.5 Level 5: System Integration Testing (E2E)

Objectives:

- Verify system interactions with external systems

- Test complete business processes across departments

- Validate data consistency across system

Entry Criteria:

- System testing complete with >90% pass rate

- All external system integrations ready

- E2E test scenarios documented

Test Scenarios:

- Complete customer journey from browse to purchase to delivery

- Admin workflows for order management and reporting

- Inventory sync with external warehousing systems

- Multi-store order processing and consolidation

Exit Criteria:

- All E2E business processes validated

- External system integrations working correctly

- Data consistency verified across all systems

4.6 Level 6: Acceptance Testing (UAT)

Objectives:

- Verify system meets business requirements

- Obtain stakeholder sign-off for release

- Identify last-minute configuration issues

Entry Criteria:

- System integration testing passed

- System in production-ready state

- UAT test cases reviewed and approved by business

Techniques:

- Business process validation

- User acceptance testing by business stakeholders

- Production data cutover testing

- Performance validation in production environment

Exit Criteria:

- Business stakeholder sign-off obtained

- 95% pass rate achieved

- Go/No-Go decision made

5. RESOURCE PLAN

5.1 Team Structure

| Role | Count | Key Responsibilities | Required Skills |
| --- | --- | --- | --- |
| Test Manager | 1 | Plan, coordinate, report | Leadership, ISTQB, Risk analysis |
| Test Lead | 2 | Supervise levels, mentor | ISTQB Advanced, Technical depth |
| QA Engineer | 6 | Test design and execution | ISTQB, Test tools, ASP.NET basics |
| Automation Engineer | 2 | Automation framework, scripts | Selenium, C#, CI/CD pipelines |
| Performance Tester | 1 | Load, stress, spike testing | JMeter, LoadRunner, profiling |
| Security Tester | 1 | Security, OWASP, compliance | Security testing, GDPR, encryption |

5.2 RACI Matrix

| Activity | Test Manager | Test Lead | QA Engineer | Automation Eng | Perf Tester | Security Tester |
| --- | --- | --- | --- | --- | --- | --- |
| Test Planning | R/A | C | I | I | I | I |
| Test Design | A | R | R | C | C | C |
| Test Automation | I | C | C | R/A | I | I |
| Execution - Functional | I | A | R | I | I | I |
| Execution - Performance | I | I | I | C | R/A | I |
| Execution - Security | I | C | C | I | I | R/A |
| Defect Management | R/A | R | R | R | C | C |
| Reporting | R/A | C | I | I | I | I |

R=Responsible, A=Accountable, C=Consulted, I=Informed

5.3 Tool Allocation

| Tool Category | Tool Name | Purpose | Assigned Team | License Count |
| --- | --- | --- | --- | --- |
| Test Management | Azure DevOps | Test case management, defect tracking | QA team + leads | 10 |
| Automation | Selenium + C# | Functional automation | Automation engineers | 2 |
| Performance | JMeter | Load and stress testing | Performance tester | 1 |
| Security | OWASP ZAP | Security scanning | Security tester | 1 |
| Accessibility | Axe/WAVE | WCAG compliance checking | QA engineers | Free/5 |
| CI/CD | GitHub Actions | Automated test execution | Automation engineers | Team |

6. NON-FUNCTIONAL TESTING

Non-functional testing covers 103 identified requirements across performance, security, usability, accessibility, and reliability dimensions.

6.1 Performance Testing

Targets:

- Page load time: <2 seconds (95th percentile)

- Concurrent users: 500 simultaneous

- Peak transaction throughput: 10,000 transactions/hour

- Database query response: <200ms (99th percentile)

Test Approach:

- Baseline testing: Establish performance metrics

- Load testing: Ramp up to 500 concurrent users

- Stress testing: Push beyond peak load

- Spike testing: Sudden load increases

- Endurance testing: 24-hour sustained load

Performance Test Scenarios:

| Scenario | Load Profile | Duration | Success Criteria | Target Metric |
| --- | --- | --- | --- | --- |
| Homepage Browse | 500 users | 1 hour | <2s load time | Page load |
| Catalog Search | 500 users | 1 hour | <3s response time | Query time |
| Checkout Peak | 100 users concurrent | 30 min | 98% successful | Transaction rate |
| Payment Processing | 50 concurrent txns | 15 min | 100% success | Throughput |
| Endurance | 250 users | 24 hours | No degradation | Memory/CPU |

6.2 Security Testing

Scope:

- OWASP Top 10 vulnerability scanning

- Authentication and authorization testing

- Encryption validation (TLS 1.2+, AES-256)

- SQL injection prevention

- XSS and CSRF protection

- GDPR compliance: data protection, right to be forgotten

- PCI DSS compliance for payment processing

Security Test Coverage:

| Vulnerability Class | Test Type | Tools | Acceptance Criteria |
| --- | --- | --- | --- |
| Injection Flaws | Manual + SAST | SonarQube, ZAP | Zero critical findings |
| Broken Auth | Manual testing | Burp Suite | All auth flows pass |
| Sensitive Data Exposure | Code review + SAST | SonarQube | All sensitive data encrypted |
| XML External Entities | Functional testing | ZAP | XXE attacks blocked |
| Access Control | Authorization testing | Manual + SAST | No privilege escalation |

6.3 Accessibility Testing

Standard: WCAG 2.1 Level AA

- Automated scanning: Axe DevTools, WAVE

- Manual testing: Keyboard navigation, screen reader compatibility

- User testing: With assistive technology users

- Color contrast validation: 4.5:1 ratio minimum

Accessibility Coverage:

| Component | Test Type | WCAG Criteria | Coverage Target |
| --- | --- | --- | --- |
| Forms | Manual + Auto | 1.3.1, 2.4.3, 3.3.1 | 100% |
| Navigation | Manual + Auto | 1.3.2, 2.4.3, 2.4.8 | 100% |
| Images | Manual + Auto | 1.1.1, 1.4.3 | 100% |
| Media | Manual | 1.2.1, 1.2.2, 1.2.3 | 100% |
| UI Components | Keyboard + Screen reader | 2.1.1, 4.1.2 | 100% |

6.4 Usability Testing

- User testing with 20 representative users

- Task completion rates: >95% target

- System Usability Scale (SUS) score: >72

- Time on task measurements

- Error rate analysis

7. END-TO-END TESTING

E2E testing validates complete business processes and system integrations across all components.

7.1 E2E Test Chains

Chain 1: Customer Purchase Journey

- Browse product catalog -> Search and filter

- Select product -> Add to cart

- View cart -> Apply discount/promotion

- Proceed to checkout -> Enter shipping address

- Select shipping method -> Enter payment details

- Process payment -> Receive order confirmation

- Email notification sent -> Order visible in dashboard

Chain 2: Admin Order Management

- View pending orders in admin dashboard

- Update order status -> Customer notified via email

- Verify inventory deduction -> Stock level updated

- Generate shipping label -> Track shipment

- Mark as delivered -> Complete order

Chain 3: Multi-Store Operations

- Create product -> Publish to store 1, store 2, store 3

- Customer purchases from store 1 -> Order routed to correct warehouse

- Inventory synced across all stores

- Reporting aggregates sales from all stores

7.2 Integration Matrix

| System A | System B | Integration Type | Data Flow | Test Cases |
| --- | --- | --- | --- | --- |
| nopCommerce | Payment Gateway | API | Order -> Payment -> Receipt | 15 |
| nopCommerce | Shipping Provider | API | Order -> Label -> Tracking | 12 |
| nopCommerce | Email Service | API | Events -> Email Notifications | 10 |
| nopCommerce | Analytics | API | Events -> Reports | 8 |
| nopCommerce | CRM | Database Sync | Customer Data -> CRM | 6 |

7.3 E2E Success Criteria

- 100% of business processes completed successfully

- Data consistency across all integrated systems

- All external system integrations working

- Email notifications delivered

- Reporting data accurate and timely

8. ENVIRONMENT PLAN

8.1 Environment Specifications

| Environment | Purpose | OS/DB | Server Specs | Data Volume | Update Frequency |
| --- | --- | --- | --- | --- | --- |
| Development | Unit & Component Testing | Windows/SQL Server | 4 vCPU, 8GB RAM | 10K records | Continuous |
| Test/QA | Integration & System Testing | Windows/SQL Server | 8 vCPU, 16GB RAM | 100K records | Daily |
| UAT | Acceptance Testing | Windows/SQL Server | 8 vCPU, 16GB RAM | 500K records | Weekly |
| Performance | Performance & Load Testing | Linux/SQL Server | 16 vCPU, 32GB RAM | 1M+ records | On-demand |
| Security | Security Testing | Windows/SQL Server | 8 vCPU, 16GB RAM | 500K records | Weekly |

8.2 Infrastructure Requirements

- Web Servers: IIS 10.0 or later

- Database: SQL Server 2019 or later

- ASP.NET Core Runtime: 6.0 or later

- Network: 1Gbps minimum, VPN for external access

- Storage: 500GB minimum for testing data

- Backup: Daily incremental, weekly full backup

8.3 Environment Setup and Maintenance

- Environments provisioned and configured 2 weeks before test start

- Daily verification of environment health and availability

- Test data refresh weekly or after major test cycles

- Performance baselines established before testing begins

9. TEST DATA STRATEGY

9.1 Data Types and Volumes

| Data Type | Record Count | Characteristics | Masking Required | Source |
| --- | --- | --- | --- | --- |
| Products | 50,000 | Various categories, prices | No | Generated |
| Customers | 10,000 | Diverse profiles, regions | Yes - PII | Masked prod data |
| Orders | 100,000 | Historical transactions | Yes - Payment | Masked prod data |
| Inventory | 50,000 | Stock levels, warehouses | No | Generated |
| Promotions | 1,000 | Active and expired codes | No | Generated |

9.2 Data Masking Policy

- Customer PII (names, emails, phone): Randomized or anonymized

- Payment information (credit cards): Tokenized or replaced with test values

- Addresses: Replaced with test addresses

- Phone numbers: Replaced with 555 test numbers

- All test data marked as test data for compliance

9.3 Data Compliance

- GDPR: No real customer data in non-production environments

- PCI DSS: No real payment card numbers in any environment

- Data retention: Test data deleted after testing cycle

- Audit trail: All test data access logged

- Regular data refresh: Monthly or after major data model changes

10. RISK MANAGEMENT

10.1 Testing Risks

| Risk ID | Risk Description | Probability | Impact | Severity | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R001 | Inadequate test coverage for complex features | Medium | High | High | Risk-based testing approach, peer reviews |
| R002 | Performance degradation under load | Medium | High | High | Early performance testing, capacity planning |
| R003 | Undetected security vulnerabilities | Low | Critical | Critical | Security testing by specialist, OWASP review |
| R004 | Data corruption during integration testing | Low | High | Medium | Isolated test environment, daily backups |
| R005 | Resource unavailability or attrition | Medium | High | High | Cross-training, contingency resources |
| R006 | Third-party integration failures | Medium | Medium | Medium | Integration testing with stubs, API contracts |

10.2 Risk Mitigation Actions

- Continuous risk monitoring throughout testing lifecycle

- Weekly risk review meetings with test team and stakeholders

- Contingency testing plans for high-risk areas

- Escalation procedures for risk threshold breaches

- Risk-based test prioritization in execution phase

11. METRICS AND REPORTING

11.1 Key Performance Indicators (KPIs)

| KPI | Target | Measurement | Reporting Frequency | Owner |
| --- | --- | --- | --- | --- |
| Test Case Execution Rate | >95% | Executed / Planned | Weekly | Test Lead |
| First-Pass Pass Rate | >90% | Pass / Total | Weekly | Test Lead |
| Defect Escape Rate | <5% | Post-release / Total | Phase end | Test Manager |
| Code Coverage | >85% | Line / Branch / Path | Weekly | Automation Eng |
| Requirement Traceability | 100% | Traced / Total | Weekly | Test Manager |
| Risk Mitigation | 100% | Addressed / Identified | Weekly | Test Manager |

11.2 Reporting Cadence

- Daily: Standup with status updates

- Weekly: Detailed test execution report

- Weekly: Defect status report

- Bi-weekly: Metrics dashboard and risk status

- Monthly: Executive summary and trend analysis

- Phase end: Test completion report with go/no-go recommendation

11.3 Metrics Dashboard

- Real-time test execution status

- Defect trend analysis and severity distribution

- Code coverage progress against targets

- Risk status and mitigation progress

- Resource utilization and schedule adherence

12. ENTRY AND EXIT CRITERIA

12.1 Organizational Entry Criteria (Pre-Testing)

- Master Test Plan approved by management

- Test team assigned and trained on project specifics

- Test environments provisioned and verified

- Test data prepared and validated

- Tools configured and integration with CI/CD pipeline

- Requirements and test cases reviewed and approved

12.2 Organizational Exit Criteria (Post-Testing)

- 95% of planned test cases executed

- 90% pass rate on first execution

- All critical defects resolved and verified

- 100% of requirements traced to passing test cases

- Code coverage >= 85% (95% for payment/security)

- All non-functional requirements validated

- Security assessment passed with zero critical findings

- GDPR compliance verified

- Accessibility compliance: WCAG 2.1 AA

- All stakeholders sign off on release

12.3 Phase-Level Entry and Exit Criteria

Unit Testing Phase

- Entry: Code review complete, CI/CD pipeline ready

- Exit: Code coverage >= 85%, all unit tests passing

Component Testing Phase

- Entry: Unit testing >= 80% complete, components ready for integration

- Exit: Component test cases >= 95% passing

Integration Testing Phase

- Entry: Component testing complete, integration test environment ready

- Exit: All integration paths validated, third-party integrations working

System Testing Phase

- Entry: Integration testing passed, system in production configuration

- Exit: 100% of functional requirements traced and tested

E2E & UAT Phase

- Entry: System testing complete, UAT environment production-ready

- Exit: Business stakeholder sign-off, go/no-go decision

APPENDIX A: BUDGET BREAKDOWN

A.1 Resource Costs

| Role | Count | Duration (weeks) | Rate/week | Total Cost |
| --- | --- | --- | --- | --- |
| Test Manager | 1 | 21 | $2,000 | $42,000 |
| Test Lead | 2 | 21 | $1,800 | $75,600 |
| QA Engineer | 6 | 21 | $1,500 | $189,000 |
| Automation Engineer | 2 | 21 | $1,700 | $71,400 |
| Performance Tester | 1 | 21 | $1,600 | $33,600 |
| Security Tester | 1 | 21 | $1,900 | $39,900 |

Total Resource Costs: $451,500

A.2 Tool and Infrastructure Costs

| Category | Item | Cost | Notes |
| --- | --- | --- | --- |
| Tools | Azure DevOps (10 users, 3 months) | $4,500 | Test management, CI/CD |
| Tools | Selenium/C# Framework Setup | $3,000 | One-time automation setup |
| Tools | JMeter & Load Gen (licenses) | $2,000 | Performance testing |
| Tools | OWASP ZAP & Security Tools | $1,500 | Security scanning |
| Infrastructure | Cloud VMs (3 months) | $15,000 | Test & performance environments |
| Data | Test Data Preparation | $5,000 | Data masking, anonymization |

Total Tool & Infrastructure Costs: $31,000

TOTAL TESTING BUDGET: $482,500

APPENDIX B: GLOSSARY

Common Terms

- Test Case: A specific test scenario with inputs, steps, and expected results

- Test Coverage: The extent to which source code or requirements are exercised by tests

- Defect: A flaw or anomaly in software that causes it to deviate from requirements

- Traceability Matrix: A document mapping requirements to test cases

- Go-Live: Release decision to move software to production

- UAT: User Acceptance Testing by business stakeholders

- E2E Testing: End-to-End testing of complete business processes

- Regression Testing: Re-testing after changes to ensure no new defects

Testing Acronyms

- MTP: Master Test Plan

- LTP: Level Test Plan

- RACI: Responsible, Accountable, Consulted, Informed

- KPI: Key Performance Indicator

- GDPR: General Data Protection Regulation

- WCAG: Web Content Accessibility Guidelines

- OWASP: Open Web Application Security Project

- PCI DSS: Payment Card Industry Data Security Standard

- NFR: Non-Functional Requirement

- SLA: Service Level Agreement

- API: Application Programming Interface

- CI/CD: Continuous Integration/Continuous Deployment