## Dashboard
Metric | Target | Status
Generated: 2026-04-06 12:40:54
Pipeline: PLANNED
Total Functional Requirements | 153
Total Features | 25
Non-Functional Requirements | 103
Test Levels | 6
Critical Requirements | 13 Must Have
Estimated Project Cost | $2,850,000
Project Duration | 12 months
Analysis Date | 2026-04-06
Quality Metrics
Code Coverage | ≥85% | Planned
Test Execution Pass Rate | ≥90% | Planned
Defect Resolution Rate | 100% | Planned
NFR Coverage | 100% | Planned
Accessibility (WCAG 2.1 AA) | 100% | Planned
Security (OWASP Top 10) | Zero Critical | Planned

## Master Test Plan
Section | Content
Document ID | MTP-NOPC-001
Version | 1.0
SCOPE AND OBJECTIVES
Business Objectives | 7
Testing Objectives | 9
In Scope Items | 13
Out of Scope Items | 9
SUCCESS CRITERIA
Requirement Coverage | 100% of 153 functional requirements
NFR Coverage | All 103 non-functional requirements
Test Execution | 95% of planned test cases executed
Pass Rate | 90% on first execution
Code Coverage | Minimum 85%
Security | Zero critical/high vulnerabilities

## Level Test Plans
Level | Level ID | Scope Summary | Key Objectives | Coverage Target | Entry Criteria Met
Unit Testing | LTP-UNIT | Individual methods, functions, and classes across nopCommerce business logic layers: User Management | 6 | 80% | 7
Component Testing | LTP-COMPONENT | Individual software components and modules: Product Service component (F05, F06, F07), Order Service | 6 | 0% | 7
Integration Testing | LTP-INTEGRATION | Interactions between integrated software components: Product Service ↔ Category Service, Order Servi | 7 | 0% | 8
System Testing | LTP-SYSTEM | Entire nopCommerce application as integrated system: all 25 features (User Mgmt F02/F15/F16/F17, Pro | 7 | 0% | 8
System Integration Testing (SIT) | LTP-SIT | Integration between nopCommerce system and external third-party systems: payment gateways (Stripe, P | 7 | 0% | 8
User Acceptance Testing (UAT) | LTP-UAT | Real business scenarios and user workflows executed by business stakeholders, merchants, and end cus | 7 | 0% | 7

## RACI Matrix
Activity | Test Manager | QA Lead | Test Automation Engineer | Manual Tester | Performance Engineer | QA Director
Test Planning | A | R |  |  |  | A
Test Design |  | A | R | C
Test Automation Development |  | R | A
Test Execution |  | C | R | R
Defect Reporting | I | C |  | R
Performance Testing |  | C | R |  | A
Security Testing | I | C |  |  | A
UAT Coordination | A | C |  |  |  | I

## Resource Allocation
Role | Allocation % | Timeline | Cost/Month | Skills Required
Test Manager | 100% | Month 1-12 (Full project) | $12,000 | Test management, Risk management, Leadership
QA Lead | 100% | Month 1-12 (Full project) | $11,000 | Test design techniques, Test automation architecture, C# and ASP.NET Core
Test Automation Engineer (Senior) | 100% | Month 2-12 (11 months) | $9,500 | Selenium WebDriver, C#/.NET, UFT/Unified Functional Testing
Test Automation Engineer (Mid-level) | 100% | Month 2-12 (11 months) | $7,500 | Selenium WebDriver, C#, Test automation best practices
Test Automation Engineer (Junior) | 100% | Month 3-12 (10 months) | $5,500 | Selenium WebDriver, C# basics, Test automation fundamentals
Manual QA Tester (Senior) | 100% | Month 1-12 (Full project) | $7,000 | Test design techniques, Business process knowledge, E-commerce domain expertise
Manual QA Tester (Mid-level) | 100% | Month 2-12 (11 months) | $5,500 | Manual testing expertise, E-commerce knowledge, SQL basics
Manual QA Tester (Mid-level) | 100% | Month 2-12 (11 months) | $5,500 | Manual testing, E-commerce domain, Defect management
Performance & Load Testing Engineer | 100% | Month 4-12 (9 months) | $10,000 | JMeter/LoadRunner expertise, Performance analysis, SQL Server tuning
Security & Compliance Tester | 100% | Month 3-12 (10 months) | $10,500 | OWASP Top 10 knowledge, PCI DSS compliance, Burp Suite/Zap expertise
Accessibility & Usability Tester | 100% | Month 3-12 (10 months) | $7,500 | WCAG 2.1 standards, Accessibility evaluation tools (Axe, WAVE), Screen reader testing (NVDA, JAWS)
DevOps/Infrastructure Engineer | 50% | Month 1-12 (Full project) | $6,000 | Azure DevOps, Docker/Containerization, SQL Server administration
Business Analyst/Domain Expert | 30% | Month 1-12 (Full project) | $4,500 | E-commerce domain expertise, nopCommerce knowledge, Requirements analysis

## Tool Allocation
Tool Category | Tool Name | Purpose | License Type | Cost

## NFT Matrix
Quality Attribute | NFR ID | Test Type | Technique | Success Criteria | Priority
Performance - Page Load | PERF-001 | Load Testing | Baseline Load Testing with Real User Monitoring | P95 <= 2000ms, P99 <= 3000ms, no errors under 500 | CRITICAL
Performance - API Response | PERF-002 | API Load Testing | RESTful API Load Testing with Transaction Monitoring | P95 <= 500ms, throughput >= 1000 req/s, error rate | CRITICAL
Performance - Search Latency | PERF-003 | Search Performance Testing | Full-Text Search Load Testing with Variability Analysis | P95 <= 300ms, relevance ranking quality score >= 0 | CRITICAL
Capacity - Concurrent Users | CAP-001 | Stress Testing | Gradual Load Increase with Resource Monitoring | Sustain 2500 CCU with acceptable degradation, auto | CRITICAL
Capacity - Data Volume | CAP-002 | Data Volume Testing | Progressive Data Load with Query Performance Analysis | Database queries P95 <= 200ms at 15GB, index fragm | CRITICAL
Availability - Uptime | AVAIL-001 | Resilience Testing | Chaos Engineering with Synthetic Monitoring | All failover scenarios execute < 60s, zero data lo | CRITICAL
Availability - Failover | AVAIL-002 | Failover Testing | Controlled Failure Injection with Automated Recovery Validation | RTO <= 60s, RPO <= 5s, automatic failover success | CRITICAL
Availability - Health Checks | AVAIL-003 | Continuous Monitoring | Synthetic Monitoring with Custom Health Endpoints | Alert latency < 30s, detection rate > 99%, false p | HIGH
Security - Encryption | SEC-001 | Security Configuration Testing | SSL/TLS Protocol Analysis with Penetration Testing | TLS 1.2+ only, SSLv3/TLSv1.0/1.1 blocked, no weak | CRITICAL
Security - Password Hashing | SEC-002 | Cryptographic Testing | Code Review and Runtime Verification of Hash Functions | All passwords use bcrypt, cost factor >= 10, no pl | CRITICAL
Security - PCI DSS Compliance | SEC-003 | Compliance Testing | PCI DSS Audit with Approved Scanning Vendor (ASV) | Pass all 12 PCI DSS requirement groups, ASV scan s | CRITICAL
Security - OWASP Top 10 (A01:2021-Broken Access Control) | SEC-004 | Penetration Testing | Authorization Bypass Testing with Privilege Escalation Attempts | No unauthorized access possible, all user roles pr | CRITICAL
Security - OWASP Top 10 (A02:2021-Cryptographic Failures) | SEC-005 | Cryptographic Analysis | Key Management Review and Encryption Strength Assessment | AES-256 for data at rest, TLS 1.2+ for transit, HS | CRITICAL
Security - OWASP Top 10 (A03:2021-Injection) | SEC-006 | Dynamic Security Testing | Parameterized Query Validation and Input Fuzzing | All queries use parameterized statements, fuzzing | CRITICAL
Security - OWASP Top 10 (A04:2021-Insecure Design) | SEC-007 | Architecture Review | STRIDE Threat Modeling and Design Review | Threat model documented, all identified threats mi | HIGH
Security - OWASP Top 10 (A05:2021-Broken Authentication) | SEC-008 | Authentication Testing | Session Hijacking, Brute Force, and Credential Replay Testing | MFA enforced for admin, session timeout < 15min, a | CRITICAL
Security - OWASP Top 10 (A06:2021-Sensitive Data Exposure) | SEC-009 | Data Exposure Testing | Log Analysis and Network Traffic Inspection | No PII/PCI data in logs, error messages sanitized, | CRITICAL
Security - OWASP Top 10 (A07:2021-Cross-Site Scripting XSS) | SEC-010 | Dynamic Web Testing | Automated XSS Payload Injection and Manual Script Validation | 0 reflected/stored XSS findings, content security | CRITICAL
Security - OWASP Top 10 (A08:2021-Software Composition Analysis) | SEC-011 | Dependency Scanning | SBOM Analysis and Vulnerability Database Matching | SBOM generated, 0 critical/high CVEs in dependenci | HIGH
Security - OWASP Top 10 (A09:2021-SSRF) | SEC-012 | Penetration Testing | URL Input Testing with Internal Service Access Attempts | SSRF prevention validated, internal IP access bloc | HIGH

## Performance Scenarios
Scenario | Concurrent Users | Duration | Ramp-up | Think Time | Expected Result
Baseline Load | 500 | 30 minutes | 5 minutes | 2-5 seconds | P95 <= 2 seconds
Stress Test | 2500 | 20 minutes | 10 minutes | 1 second | Sustain with degradation
Spike Test | 5000 | 5 minutes | 1 minute | 0 seconds | Handle and recover
Endurance Test | 1000 | 4 hours | 10 minutes | 3 seconds | No memory leaks
Peak Load | 10000 | 10 minutes | 5 minutes | 1 second | Graceful degradation

## Security Test Plan
OWASP Category | PCI DSS Requirement | Test Approach | Tools | Status
Injection Attacks | Req 6.5.1 | SQL Injection testing with SQLMap | SQLMap, Burp Suite | Planned
Authentication | Req 6.5.10 | Authentication bypass testing | Burp Suite, custom scripts | Planned
Sensitive Data Exposure | Req 3.2 | Encryption and data protection audit | Burp Suite, OpenSSL | Planned
XML External Entities | Req 6.5.1 | XXE vulnerability testing | OWASP ZAP, Burp Suite | Planned
Broken Access Control | Req 6.5.10 | Authorization testing | Burp Suite, custom scripts | Planned
Security Misconfiguration | Req 2.1 | Configuration audit | Nessus, OpenVAS | Planned
Insecure Deserialization | Req 6.5.1 | Deserialization exploit testing | Custom payloads, Burp | Planned
Using Components with Vulnerabilities | Req 6.2 | Dependency scanning | Snyk, OWASP Dependency | Planned
Insufficient Logging/Monitoring | Req 10.1 | Log audit and alerting | Manual review, ELK | Planned
Broken Cryptography | Req 3.2/3.4 | Cryptographic algorithm audit | OpenSSL, custom tools | Planned

## E2E Chain Cards
Chain ID | Chain Name | Actor | Priority | Features Involved | Step Count
E2E-001 | New Customer Registration to First Purchase | New Customer | Critical | 8 | 16
E2E-002 | Returning Customer Quick Purchase | Returning Customer | Critical | 7 | 11
E2E-003 | Product Search, Review, and Wishlist Management | Registered Customer | High | 4 | 9
E2E-004 | Admin Order Processing and Fulfillment | Admin User / Order Fulfillment Specialist | Critical | 4 | 9
E2E-005 | Payment Processing and Error Handling | Customer during Checkout | Critical | 2 | 9
E2E-006 | Customer Support - Contact Form and Ticket Management | Customer with Inquiry | High | 2 | 10
E2E-007 | Inventory Management and Low-Stock Alerts | Admin / Inventory Manager | High | 2 | 8
E2E-008 | Customer Returns and Refunds | Customer initiating return | High | 2 | 11
E2E-009 | Email Newsletter Signup and Promotional Campaign | Customer/Prospect | Medium | 2 | 12
E2E-010 | Multi-Currency and Multi-Language Product Browsing | International Customer | Medium | 4 | 10

## Integration Matrix
System | Web Portal | SQL Server | Payment Gateway | Email Service | Shipping API | CDN | Redis Cache
Web Portal |  | Test | Test | Test | Test | Test | Test
SQL Server | Test |  | Test | Test | Test | Test | Test
Payment Gateway | Test | Test |  | Test | Test | Test | Test
Email Service | Test | Test | Test |  | Test | Test | Test
Shipping API | Test | Test | Test | Test |  | Test | Test
CDN | Test | Test | Test | Test | Test |  | Test
Redis Cache | Test | Test | Test | Test | Test | Test

## Environment Specs
Environment | Purpose | Max Users | Topology | Cost/Month
Development (Dev) | Unit and component testing, local development | 10 | 5 components | $0
Component Test (CI) | Component and integration testing via CI/CD pipeli | 20 | 5 components | $150
Integration Test (Staging) | Integration testing; validates system components a | 100 | 5 components | $800
System Test (QA) | Functional, regression, and smoke testing; validat | 500 | 5 components | $2,000
Performance Test (Load/Stress) | Performance, load, stress, and endurance testing; | 2500 | 7 components | $5,000
System Integration Test (SIT) | Pre-production validation; tests integration with | 300 | 6 components | $3,500
User Acceptance Test (UAT) | Final production-equivalent validation; end-user a | 500 | 7 components | $4,000

## Test Data Strategy
Data Type | Volume | Generation Method | Compliance Level | Refresh Frequency
Customers (Core) | 100,000 records | Synthetic generation with Faker library (names, em | GDPR Level 1 + PCI DSS | Weekly (full refresh on Monday)
Products (Catalog) | 50,000 products | Deterministic generation from templates with rando | No compliance restrictions | Monthly (catalog stability needed for consistency)
Product Variants | 250,000+ variants | Combinatorial generation from base products (size/ | Non-sensitive | On-demand with product catalog refresh
Orders (Transactions) | 1,000,000+ transactions | Synthetic generation with realistic distribution ( | PCI DSS Level 1 + GDPR | Weekly (cumulative load for performance testing)
Order Line Items | 1,500,000+ items | Associated with parent orders; Quantities from 1-1 | Non-sensitive (pricing is business data) | With order refresh
Payment Tokens | 150,000 tokens | Tokenized test card numbers; No real payment crede | PCI DSS Level 1 (MANDATORY - NO REAL CARD DATA) | On-demand for specific payment scenarios
Addresses (Billing/Shipping) | 300,000+ addresses | Generated by country (70% US, 15% EU, 10% Asia, 5% | GDPR Level 1 | Weekly with customer refresh
Shopping Carts (Session Data) | 50,000 active carts | Random product selection (1-20 items per cart); Ca | Non-sensitive | Hourly (real-time test scenario simulation)
Wishlists | 200,000 wishlists | 80% customers have wishlists with 3-15 products; R | GDPR Level 2 | Weekly
Product Reviews | 150,000 reviews | 1 review per 6-7 orders; Ratings 1-5; Review text | GDPR Level 2 | Weekly with order refresh
Product Categories | 500+ categories | Pre-defined hierarchical structure (Electronics, C | Non-sensitive | Monthly or on-demand
Manufacturers | 5,000+ manufacturers | Mix of real manufacturer names (non-PII) and synth | Non-sensitive | Monthly
Customer Segments/Groups | 100+ segments | Algorithmic segmentation (VIP, Premium, Standard, | GDPR Level 2 | Weekly
Promotional Codes/Discounts | 10,000+ codes | Synthetic codes (PROMO-{ID}, SAVE{amount}, VIP{tie | Non-sensitive | On-demand per promotion campaign
Audit Logs (Access & Changes) | 10,000,000+ log entries | Automatic capture of all data access, modification | GDPR Level 1 (audit trail requirement) | Real-time capture
Data Deletion Queue | Varies (compliance requirement) | Test scenarios for right-to-be-forgotten; Schedule | GDPR Level 1 (mandatory) | On-demand per compliance request

## Data Masking Policy
PII Classification | Data Element | Masking Method | Compliance | Owner
Level 1 - Highest Risk | Email Addresses | Hash with salt or replace with test@example.com | GDPR, CCPA | Data QA Team
Level 1 - Highest Risk | Phone Numbers | Anonymize or randomize | GDPR, CCPA | Data QA Team
Level 1 - Highest Risk | Payment Card Data | Replace with test tokens (NO REAL CARDS) | PCI DSS Level 1 | Security Team
Level 2 - High Risk | Customer Names | Replace with Faker names | GDPR | Data QA Team
Level 2 - High Risk | Addresses | Replace with Faker addresses | GDPR | Data QA Team
Level 3 - Medium Risk | IP Addresses | Replace with sanitized IPs | GDPR | Data QA Team
Level 4 - Low Risk | Product Names | No masking (non-sensitive) | N/A | Product QA Team
Level 4 - Low Risk | Order IDs | Replace with sequential IDs | N/A | Performance QA Team

## Budget Breakdown
Category | Monthly Cost | Duration (Months) | Total Cost | % of Budget
Personnel (Salaries) | $65,000 | 12 | $780,000 | 27.4%
Test Automation Tools | $5,000 | 12 | $60,000 | 2.1%
Performance Testing Tools | $3,000 | 12 | $36,000 | 1.3%
Cloud Infrastructure | $3,500 | 12 | $42,000 | 1.5%
Development/Test Environments | $2,000 | 12 | $24,000 | 0.8%
Training & Consulting | $10,000 | 6 | $60,000 | 2.1%
Third-party Integrations | $2,000 | 12 | $24,000 | 0.8%
Buffer & Contingency | $0 | 0 | $1,824,000 | 64.0%
TOTAL BUDGET |  |  |  | $2,850,000

## Schedule & Milestones
Phase | Start Month | End Month | Duration (Weeks) | Key Milestones | Status
Test Planning & Strategy | 1 | 1 | 4 | MTP approved, LTP drafted | Planned
Test Design & Framework | 2 | 3 | 8 | Automation framework ready, test cases written | Planned
Unit & Component Testing | 2 | 6 | 18 | 80% code coverage, all components tested | Planned
Integration Testing | 4 | 7 | 16 | All integrations verified | Planned
System & Regression Testing | 6 | 10 | 20 | Full regression suite passing | Planned
Performance & Security Testing | 7 | 11 | 16 | Performance baselines, security audit complete | Planned
UAT Preparation & Execution | 10 | 12 | 8 | UAT sign-off, final go/no-go | Planned
Post-Release Support | 12 | 12 | 4 | Go-live, critical defect monitoring | Planned