## Dashboard
nopCommerce STRATEGY Test Design Dashboard
Analysis Date: | 2026-04-06
Agent Results
Scope & Technique | S_scope, T_technique
Risk & Approach | R_risk, A_approach
Testability & Estimation | T_testability, E_estimation
Governance & Yield | G_governance, Y_yield
Risk Profile Summary
Total Risks Identified | 32
Critical Risks (A) | 11
High Risks (B) | 14
Medium Risks (C) | 7
Risk Exposure Score | 8.4
Quality Metrics
Overall Quality Score | 72.1
Correctness | 72
Unambiguous | 65
Complete | 74
Consistent | 68
Ranked | 88
Verifiable | 62
Modifiable | 78
Traceable | 70

## Scope Statement
Type | Item
In-Scope | Product discovery and search functionality (F05, F06, F07, F22, F23) with multi-language support
In-Scope | User registration, login, and account management (F02, F15, F16, F17) with GDPR compliance
In-Scope | Shopping cart and order management (F03, F04, F08, F09) including add-to-cart, updates, checkout flow
In-Scope | Payment processing and multiple payment gateways (F10, F11, F12, F13, F14)
In-Scope | Wishlist functionality with full test coverage (17 test cases from OpenTest)
In-Scope | Product catalog and inventory management with real-time stock updates
In-Scope | Checkout process including shipping, tax calculation, and order confirmation
In-Scope | Performance requirements: latency <500ms (p95), capacity 10K concurrent users, 99.9% availability
In-Scope | Security requirements: HTTPS/TLS 1.3, GDPR data retention policies, PCI-DSS compliance
In-Scope | Localization and multi-currency support (F01, F25)
In-Scope | Content management system for promotional content (F18, F19, F20, F21)
In-Scope | User authentication via OAuth 2.0 and local credentials
In-Scope | Integration with payment providers (Stripe, PayPal, etc.)
In-Scope | Database layer: SQL Server with optimized queries and indexing strategies
In-Scope | Caching strategy: Redis for session management and product data
In-Scope | API endpoints: REST APIs for all product, user, order, and payment operations
In-Scope | Accessibility standards: WCAG 2.1 Level AA compliance
In-Scope | Monitoring and logging infrastructure with real-time alerting
In-Scope | Admin dashboard for order and product management
In-Scope | Email notifications for order confirmation and shipping updates
Out-of-Scope | Third-party integration with external marketing automation platforms
Out-of-Scope | Machine learning-based recommendation engine (future enhancement)
Out-of-Scope | Mobile app development (web-only scope)
Out-of-Scope | Social media integration beyond basic sharing
Out-of-Scope | Advanced analytics and business intelligence dashboards
Out-of-Scope | Custom ERP system integration
Out-of-Scope | Multi-tenancy support for SaaS deployments
Out-of-Scope | Voice commerce or conversational AI features

## Test Objects
Test Object ID | Name | Type | Features | Quality Characteristics
TO-001 | User Registration Module | UI | F02, F15 | Functional Suitability, Usability, Security
TO-002 | User Login Service | API | F02 | Functional Suitability, Security, Performance
TO-003 | Product Search UI | UI | F05, F06 | Functional Suitability, Performance, Usability
TO-004 | Product Search API | API | F05, F06 | Functional Suitability, Performance
TO-005 | Shopping Cart Component | UI | F03, F04 | Functional Suitability, Usability
TO-006 | Shopping Cart Service | API | F03 | Functional Suitability, Performance
TO-007 | Checkout Process | UI | F08, F09 | Functional Suitability, Usability, Security
TO-008 | Payment Processing Service | Integration | F10, F11, F12 | Functional Suitability, Security, Reliability
TO-009 | Order Management API | API | F13, F14 | Functional Suitability, Performance
TO-010 | Wishlist Feature | UI | F22 | Functional Suitability, Usability
TO-011 | Wishlist API | API | F22 | Functional Suitability, Performance
TO-012 | Product Catalog Database | Database | F05, F06, F07 | Functional Suitability, Reliability
TO-013 | User Account Database | Database | F02, F15, F16, F17 | Functional Suitability, Reliability, Security
TO-014 | Order Database | Database | F13, F14 | Functional Suitability, Reliability
TO-015 | Product Filter UI | UI | F07, F23 | Functional Suitability, Usability
TO-016 | Category Navigation | UI | F05 | Functional Suitability, Usability
TO-017 | Multi-Currency Service | Service | F25 | Functional Suitability, Usability
TO-018 | Localization Service | Service | F01 | Functional Suitability, Usability
TO-019 | Content Management System | UI | F18, F19, F20, F21 | Functional Suitability, Usability
TO-020 | Admin Dashboard | UI | F16 | Functional Suitability, Usability
TO-021 | Email Notification Service | Service | F09, F14 | Functional Suitability, Reliability
TO-022 | Redis Cache Layer | Integration | F05, F06 | Performance, Reliability
TO-023 | Session Management | Service | F02, F15 | Security, Reliability
TO-024 | Shipping Integration | Integration | F09 | Functional Suitability, Reliability
TO-025 | Tax Calculation Engine | Service | F09 | Functional Suitability, Accuracy
TO-026 | Product Review System | UI | F07 | Functional Suitability, Usability
TO-027 | Account Settings Page | UI | F15, F17 | Functional Suitability, Usability, Security

## Quality Characteristics
Characteristic | Sub-Characteristics | Relevance | Test Objects | Priority
Functional Suitability | Completeness, Correctness, Appropriateness | High | TO-001, TO-002, TO-003, TO-004, TO-005, TO-006, TO-007, TO-008, TO-009, TO-010, TO-011, TO-012, TO-013, TO-014, TO-015, TO-016, TO-019, TO-020, TO-024, TO-025, TO-026 | 1
Performance Efficiency | Time Behaviour, Resource Utilisation, Capacity | High | TO-002, TO-004, TO-006, TO-022 | 2
Compatibility | Co-existence, Interoperability | Medium | TO-008, TO-022, TO-024 | 4
Usability | Learnability, Operability, User Error Protection, User Interface Aesthetics, Accessibility | High | TO-001, TO-003, TO-005, TO-007, TO-015, TO-016, TO-017, TO-018, TO-019, TO-020, TO-026, TO-027 | 2
Reliability | Maturity, Availability, Fault Tolerance, Recoverability | High | TO-008, TO-009, TO-012, TO-013, TO-014, TO-021, TO-022, TO-023, TO-024 | 3
Security | Confidentiality, Integrity, Non-Repudiation, Accountability, Authenticity | High | TO-001, TO-002, TO-007, TO-008, TO-013, TO-023, TO-027 | 1
Maintainability | Modularity, Reusability, Analysability, Modifiability, Testability | Medium | TO-002, TO-004, TO-006, TO-009, TO-011 | 5
Portability | Adaptability, Installability, Replaceability | Low | TO-022 | 6

## Technique Matrix
Technique ID | Technique Name | Category | Applicable To | Coverage Group | Intensity | Est. Test Cases | Effort Factor
T-001 | Boundary Value Analysis | Specification | TO-005, TO-006, TO-025 | CG-03 | Thorough | 24 | 1.5
T-002 | Equivalence Partitioning | Specification | TO-001, TO-003, TO-004, TO-015, TO-017 | CG-02 | Standard | 18 | 1.2
T-003 | Decision Table Testing | Specification | TO-007, TO-008, TO-025 | CG-05 | Thorough | 12 | 1.8
T-004 | State Transition Testing | Structure | TO-005, TO-006, TO-010, TO-011 | CG-06 | Standard | 16 | 1.6
T-005 | Pairwise Testing | Structure | TO-003, TO-015 | CG-02 | Standard | 20 | 1.4
T-006 | Combinatorial Testing | Structure | TO-007, TO-009 | CG-05 | Thorough | 32 | 2
T-007 | Use Case Testing | Specification | TO-001, TO-002, TO-005, TO-007, TO-010 | CG-01 | Thorough | 28 | 1.7
T-008 | Scenario Testing | Experience | TO-005, TO-007, TO-009 | CG-03 | Standard | 15 | 1.3
T-009 | User Journey Testing | Experience | TO-005, TO-007, TO-020 | CG-03 | Standard | 12 | 1.5
T-010 | Exploratory Testing | Experience | TO-001, TO-003, TO-005, TO-007, TO-015, TO-020 | CG-11 | Standard | 20 | 1.8
T-011 | API Contract Testing | Specialized | TO-002, TO-004, TO-006, TO-009, TO-011 | CG-07 | Thorough | 22 | 1.4
T-012 | Database Testing | Specialized | TO-012, TO-013, TO-014 | CG-08 | Thorough | 26 | 1.6
T-013 | SQL Injection Testing | Specialized | TO-013, TO-014 | CG-12 | Thorough | 14 | 1.5
T-014 | Cross-Site Scripting (XSS) Testing | Specialized | TO-001, TO-005, TO-019, TO-020 | CG-01 | Thorough | 18 | 1.6
T-015 | CSRF Token Validation | Specialized | TO-001, TO-002 | CG-01 | Thorough | 10 | 1.3
T-016 | Authentication Bypass Testing | Specialized | TO-002, TO-023 | CG-01 | Thorough | 16 | 1.7
T-017 | Session Management Testing | Specialized | TO-023 | CG-01 | Thorough | 12 | 1.5
T-018 | PCI-DSS Compliance Testing | Domain | TO-008 | CG-04 | Thorough | 20 | 2.2
T-019 | Payment Gateway Integration Testing | Integration | TO-008 | CG-04 | Thorough | 24 | 2
T-020 | Load Testing | Specialized | TO-002, TO-004, TO-006 | CG-07 | Thorough | 8 | 2.5
T-021 | Stress Testing | Specialized | TO-004, TO-006 | CG-07 | Thorough | 6 | 2.3
T-022 | Endurance Testing | Specialized | TO-022, TO-023 | CG-07 | Standard | 4 | 3
T-023 | WCAG Accessibility Testing | UX | TO-001, TO-003, TO-005, TO-007, TO-015, TO-016, TO-019, TO-020 | CG-09 | Standard | 32 | 1.8
T-024 | Screen Reader Testing | UX | TO-001, TO-005, TO-007 | CG-09 | Standard | 16 | 2
T-025 | Keyboard Navigation Testing | UX | TO-005, TO-007, TO-015, TO-020 | CG-09 | Standard | 14 | 1.6
T-026 | Localization Testing | Domain | TO-017, TO-018 | CG-10 | Standard | 18 | 1.7
T-027 | Currency Conversion Testing | Domain | TO-017 | CG-10 | Standard | 12 | 1.4
T-028 | GDPR Data Privacy Testing | Domain | TO-013 | CG-12 | Thorough | 16 | 1.9
T-029 | Right-to-Deletion Testing | Domain | TO-013 | CG-12 | Thorough | 10 | 1.6
T-030 | Error Message Testing | UX | TO-001, TO-005, TO-007, TO-019, TO-020 | CG-11 | Standard | 14 | 1.2
T-031 | Transaction Rollback Testing | Specialized | TO-008, TO-009, TO-014 | CG-08 | Thorough | 14 | 1.8
T-032 | Concurrency Testing | Specialized | TO-005, TO-006, TO-009 | CG-08 | Thorough | 12 | 2.1
T-033 | Inventory Synchronization Testing | Specialized | TO-006, TO-012 | CG-08 | Thorough | 16 | 1.9
T-034 | Coupon and Discount Calculation | Domain | TO-005, TO-025 | CG-05 | Standard | 20 | 1.5
T-035 | Tax Calculation Accuracy | Domain | TO-025 | CG-05 | Thorough | 18 | 1.7
T-036 | Shipping Cost Calculation | Domain | TO-024 | CG-05 | Standard | 14 | 1.5
T-037 | Cache Invalidation Testing | Specialized | TO-022 | CG-07 | Standard | 10 | 1.6
T-038 | Email Notification Testing | Integration | TO-021 | CG-05 | Standard | 12 | 1.4
T-039 | Product Search Relevance | UX | TO-003, TO-004 | CG-02 | Standard | 16 | 1.5
T-040 | Filter and Sort Functionality | UX | TO-015 | CG-02 | Standard | 18 | 1.4
T-041 | Wishlist Persistence Testing | Specialized | TO-010, TO-011 | CG-06 | Standard | 10 | 1.3
T-042 | Cart Recovery Testing | Specialized | TO-005, TO-006 | CG-03 | Standard | 8 | 1.5
T-043 | Product Page Load Performance | Specialized | TO-003, TO-004 | CG-07 | Standard | 8 | 1.3
T-044 | Checkout Page Latency Testing | Specialized | TO-007 | CG-07 | Thorough | 6 | 1.4
T-045 | API Response Time Testing | Specialized | TO-002, TO-004, TO-006, TO-009 | CG-07 | Standard | 12 | 1.3
T-046 | Responsive Design Testing | UX | TO-001, TO-003, TO-005, TO-007, TO-015, TO-020 | CG-09 | Standard | 20 | 1.6
T-047 | Cross-Browser Testing | UX | TO-001, TO-003, TO-005, TO-007, TO-020 | CG-09 | Standard | 22 | 1.8
T-048 | Account Recovery Testing | Specialized | TO-001, TO-002 | CG-01 | Standard | 8 | 1.4
T-049 | Two-Factor Authentication Testing | Specialized | TO-002 | CG-01 | Thorough | 14 | 1.6
T-050 | Admin Account Privilege Testing | Specialized | TO-020 | CG-01 | Thorough | 12 | 1.5

## Feature-Technique Map
Feature ID | Feature Name | Applicable Techniques | Recommended Primary | Recommended Secondary
F01 | Localization - Language Support | T-026, T-023, T-024, T-025 | T-026 | T, -, 0, 2, 3
F02 | User Registration & Login | T-001, T-007, T-014, T-015, T-016, T-017, T-048, T-049 | T-007 | T, -, 0, 1, 6
F03 | Add to Cart | T-001, T-002, T-008, T-032, T-042 | T-008 | T, -, 0, 3, 2
F04 | Update Cart | T-001, T-004, T-008, T-032 | T-004 | T, -, 0, 3, 2
F05 | Product Catalog - Browse | T-002, T-005, T-010, T-023, T-039, T-043 | T-010 | T, -, 0, 3, 9
F06 | Product Search | T-002, T-005, T-011, T-039, T-043 | T-039 | T, -, 0, 1, 1
F07 | Product Filtering & Reviews | T-002, T-005, T-010, T-040 | T-040 | T, -, 0, 1, 0
F08 | Checkout Process | T-003, T-006, T-007, T-008, T-009, T-023, T-044 | T-007 | T, -, 0, 4, 4
F09 | Shipping & Delivery | T-003, T-034, T-035, T-036 | T-036 | T, -, 0, 3, 5
F10 | Payment Methods - CC | T-013, T-018, T-019 | T-019 | T, -, 0, 1, 8
F11 | Payment Methods - Digital Wallets | T-018, T-019 | T-019 | T, -, 0, 1, 8
F12 | Payment Methods - Bank Transfer | T-018, T-019 | T-019 | T, -, 0, 1, 8
F13 | Order Management - Tracking | T-004, T-012, T-031 | T-012 | T, -, 0, 3, 1
F14 | Order Management - Cancellation | T-004, T-031 | T-031 | T, -, 0, 0, 4
F15 | Account Management - Profile | T-023, T-025, T-030 | T-030 | T, -, 0, 2, 3
F16 | Account Management - Admin | T-050 | T-050 | T, -, 0, 1, 6
F17 | Account Settings & Preferences | T-023, T-025 | T-023 | T, -, 0, 2, 5
F18 | CMS - Homepage | T-010, T-023, T-046 | T-010 | T, -, 0, 4, 6
F19 | CMS - Category Pages | T-010, T-023 | T-010 | T, -, 0, 2, 3
F20 | CMS - Promotional Content | T-010, T-046 | T-010 | T, -, 0, 4, 6
F21 | CMS - Static Pages | T-010, T-023 | T-010 | T, -, 0, 2, 3
F22 | Wishlist - Add/Remove | T-004, T-041 | T-041 | T, -, 0, 0, 4
F23 | Product Recommendations | T-002, T-010 | T-010 | T, -, 0, 0, 2
F24 | Order Confirmation Emails | T-038 | T-038 | T, -, 0, 0, 7
F25 | Multi-Currency Support | T-027 | T-027 | T, -, 0, 2, 6

## Risk Register
Risk ID | Description | Test Object | Quality Char | Probability | Impact | Score | Class | Mitigation
QR-001 | Payment gateway communication failures with no automatic retry mechanism | Checkout/Payment module - Stripe & PayPal integration | Reliability | High | High | 10 | A | Implement transactional retry logic with exponential backoff; add circuit breaker pattern; establish payment reconciliation processes; add detailed logging and monitoring
QR-002 | Stock inventory race conditions during concurrent purchases | Shopping module - inventory reservation system | Reliability | High | High | 9 | A | Implement pessimistic locking or optimistic locking with proper conflict resolution; add load testing at 2,500 peak users; establish inventory synchronization protocols
QR-003 | PCI DSS compliance gaps - sensitive payment data handling vulnerabilities | Checkout/Payment module - payment data flow | Security | High | High | 10 | A | Implement tokenization for all payment data; enforce TLS 1.2+ encryption; add comprehensive security audit; implement PCI DSS 3.2.1 compliance checks
QR-004 | GDPR compliance gaps - insufficient audit logging for data access and processing | User Management module - personal data access logging | Security | High | High | 9 | A | Implement comprehensive audit logging for all PII access; add data retention policies; implement user consent management; establish GDPR compliance verification
QR-005 | Missing audit trail for critical administrative operations | User Management module - admin operations | Reliability | High | Medium | 8 | A | Add comprehensive audit logging for all admin actions; implement tamper-evident audit logs; establish log retention policies; add monitoring and alerting
QR-006 | Authentication bypass vulnerabilities in user login mechanism | User Management module - authentication layer | Security | Medium | High | 8 | A | Implement rate limiting on login attempts; add CAPTCHA after failed attempts; add multi-factor authentication option; conduct security code review
QR-007 | SQL injection vulnerabilities in product search and filtering | Product Discovery module - search queries | Security | Medium | High | 8 | A | Enforce parameterized queries; implement input validation and sanitization; add SAST scanning; conduct security penetration testing
QR-008 | Cross-Site Scripting (XSS) in product descriptions and user-generated content | Product Discovery module - content display | Security | Medium | High | 8 | A | Implement output encoding; add CSP headers; sanitize all user input; implement security code review and automated scanning
QR-009 | Page load time exceeds 2-second SLA during peak traffic (500-2500 users) | Shopping/Product Discovery modules - performance under load | Performance Efficiency | High | Medium | 8 | A | Implement database query optimization; add caching strategy (Redis); implement CDN for static assets; conduct load testing at 2,500 concurrent users
QR-010 | Uptime degradation below 99.9% SLA during seasonal peak traffic | All modules - system availability | Reliability | Medium | High | 8 | A | Implement horizontal scaling; add load balancing; implement health checks and auto-failover; conduct sustained load testing and chaos engineering
QR-011 | Payment gateway integration failures with Stripe or PayPal APIs | Checkout/Payment module - gateway integration | Interoperability | Medium | High | 8 | A | Implement comprehensive mock/stub testing; add fallback payment methods; implement dependency resilience patterns; establish vendor SLA monitoring
QR-012 | Shipping carrier integration failures (UPS/FedEx API timeouts) | Checkout/Payment module - shipping integration | Interoperability | Medium | Medium | 7 | B | Implement timeout handling and graceful degradation; add alternate carrier selection; implement circuit breaker pattern for API calls
QR-013 | Email delivery failures for order confirmations and shipping notifications | Content/Notification module - SMTP integration | Interoperability | Medium | Medium | 7 | B | Implement email queue with retry logic; add monitoring for SMTP failures; implement fallback notification channels; add delivery tracking
QR-014 | Tax calculation errors due to complex multi-jurisdiction rules | Checkout/Payment module - tax service integration | Correctness | Medium | Medium | 7 | B | Create comprehensive tax rule test data; implement tax calculation verification; add jurisdiction coverage matrix; establish reconciliation procedures
QR-015 | Product catalog inconsistency between database and CDN cache | Product Discovery module - caching layer | Reliability | Medium | Medium | 7 | B | Implement cache invalidation strategy; add consistency verification tests; implement eventual consistency monitoring
QR-016 | Localization errors in multi-language product content | Localization module - content translation | Usability | Medium | Medium | 7 | B | Implement translation quality gates; add linguistic testing for all supported languages; establish translation verification process
QR-017 | Currency conversion accuracy and rounding errors in multi-currency transactions | Localization/Checkout module - currency handling | Correctness | Medium | Medium | 7 | B | Implement decimal precision testing; add currency rounding verification; establish exchange rate update procedures
QR-018 | Discount code exploitation through concurrent application attempts | Shopping module - promotion/coupon system | Security | Medium | Medium | 7 | B | Implement discount limit enforcement with locking; add fraud detection rules; implement concurrent access controls
QR-019 | Cross-site request forgery (CSRF) vulnerabilities in form submissions | User Management/Shopping modules - form handling | Security | Low | High | 6 | B | Implement CSRF tokens in all forms; add SameSite cookie attributes; implement security code review
QR-020 | Insecure password reset mechanism allowing account takeover | User Management module - password reset flow | Security | Medium | High | 7 | B | Implement secure token generation and expiration; add rate limiting; implement verification email with one-time links
QR-021 | Database backup and disaster recovery testing insufficient | Infrastructure - backup and recovery | Reliability | Low | High | 6 | B | Implement regular backup verification testing; conduct DR drills quarterly; establish RTO/RPO targets
QR-022 | Mobile app responsive design breaks on smaller screens | All modules - responsive UI | Usability | Medium | Medium | 6 | B | Implement automated responsive testing; test on actual devices; implement progressive enhancement
QR-023 | API rate limiting not implemented allowing DoS attacks | All API endpoints - rate limiting | Security | Medium | Medium | 7 | B | Implement per-IP and per-user rate limiting; add DDoS protection; implement monitoring and alerting
QR-024 | Session hijacking vulnerability through insecure session management | User Management module - session handling | Security | Low | High | 6 | B | Implement secure session tokens; add IP validation; implement HTTPS-only cookies with secure flag
QR-025 | Order confirmation delay causing customer confusion | Checkout/Payment module - order creation | Performance Efficiency | Low | Medium | 5 | C | Implement async order processing; add real-time order status updates; implement notification retry logic
QR-026 | Incorrect order total calculation under specific discount combinations | Shopping module - discount calculation logic | Correctness | Low | Medium | 5 | C | Create comprehensive discount combination test matrix; implement calculation verification; add audit logging
QR-027 | Product variant selection allowing invalid combinations | Product Discovery module - variant handling | Correctness | Low | Medium | 5 | C | Implement variant constraint validation; add dependency matrix testing; implement UI constraint enforcement
QR-028 | Search results relevance issues in product discovery | Product Discovery module - search algorithm | Usability | Low | Medium | 5 | C | Implement search quality metrics; conduct user acceptance testing; establish relevance baseline
QR-029 | Accessibility compliance failures for WCAG 2.1 AA | All modules - accessibility features | Usability | Medium | Medium | 6 | B | Implement automated accessibility scanning; add screen reader testing; conduct accessibility audit
QR-030 | Browser compatibility issues across Chrome, Firefox, Safari, Edge | All modules - cross-browser functionality | Compatibility | Medium | Medium | 6 | B | Implement cross-browser testing automation; add manual testing on target browsers; establish compatibility matrix
QR-031 | Third-party library vulnerabilities not detected or patched | Infrastructure - dependency management | Security | High | Medium | 8 | A | Implement SCA (Software Composition Analysis); add automatic vulnerability scanning; establish patching SLA
QR-032 | Memory leaks in long-running processes affecting availability | Infrastructure - system reliability | Reliability | Low | High | 6 | B | Implement memory profiling; add long-running process monitoring; conduct stress testing

## Risk Heatmap
Risk Class | Count | Testing Approach | Coverage Target
A (Critical) | 11 | Thorough & Exhaustive | 95-100%
B (High) | 14 | Comprehensive | 80-95%
C (Medium) | 7 | Standard | 70-80%

## Test Strategy Table
Quality Characteristic | Risk Class | Recommended Techniques | Coverage Target | Entry Criteria | Exit Criteria
Functionality/Correctness | A |  |  | Requirements specification complete and reviewed, Design documents approved, Test data prepared, Test environment available | 95% functional coverage achieved, All critical bugs resolved, Test execution report approved, Sign-off from business owner
Reliability | A |  |  | Performance requirements defined and baselined, Test infrastructure prepared (load generation tools), Production-like environment available, Monitoring and alerting configured | 99.9% uptime achieved in 24-hour sustained test, All critical failures < 5 minute recovery, Mean time between failures (MTBF) documented, Performance baseline established
Security | A |  |  | Security requirements defined (PCI DSS, GDPR), Threat model completed, Security tools configured and validated, Penetration testing scope defined | Zero critical vulnerabilities, All OWASP Top 10 tested and mitigated, PCI DSS compliance audit passed, GDPR compliance audit passed, Security penetration test report approved
Performance Efficiency | A |  |  | Performance SLAs defined (<2s page load), Baseline metrics established, Load testing environment configured, Monitoring tools deployed | Page load time < 2 seconds at 500 avg users, Page load time < 2.5 seconds at 2500 peak users, Database response time < 200ms (95th percentile), CPU utilization < 75% at peak load
Usability | B |  |  | Usability requirements defined, Test users/personas identified, Accessibility requirements defined (WCAG 2.1 AA), Test environment available | WCAG 2.1 AA compliance achieved, Usability issues with medium/high severity resolved, Mobile responsiveness verified across devices, Localization quality approved
Compatibility | B |  |  | Target browser/OS/device matrix defined, Test environment configured for all targets, Automation framework for compatibility testing setup | 95% functional coverage across all browsers, Critical functionality working on all supported platforms, Performance acceptable across platforms, Compatibility matrix documented
Maintainability | B |  |  | Code coverage tools configured, Code quality baseline established, Development standards documented | Code coverage > 80% for critical modules, Cyclomatic complexity < 10 for methods, No high-severity code quality violations, Test automation framework established
Portability | C |  |  | Target deployment environments identified, Deployment automation scripts prepared, Configuration management strategy defined | Successful deployment to all target environments, Configuration portability verified, Data migration validated, Deployment documentation completed

## QE Strategy
Quality Characteristic | Prevention | Static Testing | Dynamic Testing | Correction/Monitoring
Functionality/Correctness | Formal requirements review with stakeholders, Detailed design specification with use cases, Code review standards and checklist, Pair programming for complex logic, Test-driven development (TDD) for payment and inventory modules |  | Equivalence partitioning with 10+ test cases per module, Boundary value analysis (edge cases, limits), Decision table testing for complex logic, State transition testing for order/payment flow, Integration testing between modules, System testing with end-to-end scenarios
Reliability | Resilience patterns implementation (retry, circuit breaker, timeout), Redundancy design for critical components, Failover mechanism testing, Health check implementation, Monitoring and alerting setup, Incident response procedures |  | Load testing (500-2500 users), Stress testing (beyond capacity), Spike testing (sudden load increase), Soak testing (24+ hour sustained load), Failover testing (component failure simulation), Chaos engineering testing (random failure injection), Recovery testing (restart scenarios)
Security | Security requirements specification, Threat modeling (STRIDE/PASTA), Secure coding guidelines, Security training for developers, Secure SDLC implementation, PCI DSS compliance controls, GDPR compliance controls, Encryption implementation for all sensitive data |  | Penetration testing (authorized third-party), OWASP Top 10 vulnerability testing, SQL injection testing (SQLmap, manual), XSS testing (multiple vectors), CSRF testing, Authentication bypass testing, Authorization access control testing, Cryptography validation testing, SSL/TLS certificate validation, Security header validation
Performance Efficiency | Performance requirements definition (SLAs: <2s page load, 99.9% uptime), Capacity planning and right-sizing, Caching strategy (Redis, CDN, browser cache), Database optimization (indexing, query optimization), Code optimization (profiling, memory management), Infrastructure optimization (load balancing, auto-scaling) |  | Response time measurement at various loads, Throughput testing (transactions per second), Load testing with realistic user profiles, Scalability testing (linear vs. degraded performance), Resource utilization profiling (CPU, memory, I/O, network), Database performance testing (query times, locks), Caching effectiveness testing, CDN performance validation
Usability | User research and persona development, Usability requirements specification, UI/UX design with accessibility in mind (WCAG 2.1 AA), Responsive design implementation, Localization planning for multiple languages, Accessibility standards training |  | User acceptance testing (UAT) with real users (5+ per scenario), Usability testing with user personas, Accessibility testing: WCAG 2.1 AA compliance, Screen reader testing (NVDA, JAWS), Keyboard navigation testing, Mobile responsiveness testing (multiple devices), Localization testing (linguistic and cultural), Exploratory testing with user scenarios
Compatibility | Target platform/browser/OS matrix definition, Progressive enhancement strategy, Graceful degradation for older browsers, API compatibility maintenance, Dependency version management, Database version compatibility |  | Cross-browser testing (Chrome, Firefox, Safari, Edge), Operating system compatibility testing, Mobile device testing (iOS, Android, various screen sizes), Third-party integration compatibility testing, API version compatibility testing, Backward compatibility testing
Maintainability | Code standards and style guide, Test automation framework establishment, Documentation standards, Version control practices, Code review process, Technical debt management |  | Regression test automation (>80% automated), Test case traceability verification, Test maintenance effort tracking, CI/CD pipeline validation, Build stability monitoring
Portability | Target deployment environment definition, Configuration management strategy, Containerization (Docker) implementation, Infrastructure as code (IaC) adoption, Database abstraction layer implementation |  | Deployment testing across environments, Configuration portability validation, Data migration testing, Rollback testing, Infrastructure elasticity testing

## Testability Assessment
Feature ID | Feature Name | Priority | Testability Score | Complexity
F01 | User Registration & Authentication | MUST_HAVE | 75 | High
F02 | Product Catalog Management | MUST_HAVE | 78 | Medium
F03 | Shopping Cart Management | MUST_HAVE | 76 | High
F04 | Order Processing & Checkout | MUST_HAVE | 72 | High
F05 | Payment Processing | MUST_HAVE | 65 | High
F06 | Inventory Management | MUST_HAVE | 74 | Medium
F07 | Order Fulfillment & Shipping | MUST_HAVE | 70 | High
F08 | Customer Account Management | SHOULD_HAVE | 77 | Medium
F09 | Search & Filtering | SHOULD_HAVE | 73 | Medium
F10 | Product Reviews & Ratings | SHOULD_HAVE | 75 | Low
F11 | Wishlist Management | SHOULD_HAVE | 78 | Low
F12 | Discount & Promotion Management | SHOULD_HAVE | 69 | High
F13 | Email Notifications | SHOULD_HAVE | 68 | Medium
F14 | Customer Reviews & Support | SHOULD_HAVE | 71 | Medium
F15 | Admin Dashboard & Analytics | SHOULD_HAVE | 70 | High
F16 | User Role & Permission Management | MUST_HAVE | 74 | Medium
F17 | API Integration Management | MUST_HAVE | 63 | High
F18 | Reporting & Export | COULD_HAVE | 72 | Medium
F19 | Multi-language Support | COULD_HAVE | 71 | Medium
F20 | Mobile App Support | COULD_HAVE | 66 | High
F21 | Advanced Search with Recommendations | COULD_HAVE | 62 | High
F22 | Social Commerce Integration | COULD_HAVE | 64 | High
F23 | Subscription Management | COULD_HAVE | 67 | High
F24 | Loyalty Program | COULD_HAVE | 70 | Medium
F25 | Security & Compliance | MUST_HAVE | 68 | High

## Effort Estimation
Technique | Test Cases | Effort Hours | Effort Factor
Total Test Points | 892
Total Effort Hours | 2676
Total Effort Person Days | 334.5
Total Effort Weeks | 67
Confidence Level | Medium (±35%)
Contingency Factor | 1.25
Contingency Hours | 669
Total With Contingency Hours | 3345
Total With Contingency Weeks | 84
Effort by Test Level
Unit Testing | 1343 | 50.1 | 340
Integration Testing | 806 | 30.1 | 120
API/Contract Testing | 268 | 10 | 85
System/E2E Testing | 134 | 5 | 35
Performance Testing | 67 | 2.5 | 15
Security Testing | 58 | 2.3 | 25
Effort by Technique
Equivalence Partitioning | 95 | 285 | 3
Boundary Value Analysis | 82 | 246 | 3
Decision Table Testing | 68 | 272 | 4
State Transition Testing | 54 | 270 | 5
Use Case Testing | 45 | 225 | 5
Pairwise Testing | 38 | 152 | 4
Property-based Testing | 35 | 175 | 5
Contract Testing | 48 | 240 | 5
API Mocking & Stubbing | 52 | 156 | 3
Load & Stress Testing | 32 | 224 | 7
Exploratory Testing | 40 | 200 | 5
Security Testing (OWASP) | 35 | 210 | 6
Regression Testing | 98 | 294 | 3
Integration Testing | 78 | 312 | 4
Database Testing | 45 | 180 | 4

## WSJF Prioritization
Rank | Feature ID | Feature Name | Business Value | Time Criticality | Risk Reduction | Job Size
1 | F04 | Order Processing & Checkout | 9 | 8 | 9 | 9
2 | F05 | Payment Processing | 10 | 9 | 10 | 8
3 | F01 | User Registration & Authentication | 9 | 9 | 8 | 7
4 | F02 | Product Catalog Management | 9 | 8 | 8 | 6
5 | F03 | Shopping Cart Management | 9 | 8 | 8 | 7
6 | F06 | Inventory Management | 8 | 8 | 9 | 5
7 | F07 | Order Fulfillment & Shipping | 8 | 7 | 8 | 7
8 | F25 | Security & Compliance | 9 | 9 | 10 | 8
9 | F16 | User Role & Permission Management | 7 | 7 | 7 | 5
10 | F12 | Discount & Promotion Management | 7 | 6 | 7 | 6
11 | F09 | Search & Filtering | 7 | 7 | 6 | 5
12 | F15 | Admin Dashboard & Analytics | 6 | 6 | 6 | 7
13 | F08 | Customer Account Management | 6 | 6 | 6 | 5
14 | F13 | Email Notifications | 6 | 6 | 5 | 5
15 | F17 | API Integration Management | 5 | 5 | 7 | 6
16 | F10 | Product Reviews & Ratings | 5 | 5 | 5 | 4
17 | F11 | Wishlist Management | 4 | 4 | 4 | 3
18 | F14 | Customer Reviews & Support | 5 | 5 | 5 | 5
19 | F18 | Reporting & Export | 4 | 4 | 4 | 4
20 | F19 | Multi-language Support | 3 | 3 | 3 | 4
21 | F20 | Mobile App Support | 5 | 6 | 6 | 7
22 | F23 | Subscription Management | 4 | 4 | 5 | 6
23 | F21 | Advanced Search with Recommendations | 3 | 4 | 4 | 7
24 | F22 | Social Commerce Integration | 3 | 3 | 3 | 6
25 | F24 | Loyalty Program | 3 | 3 | 3 | 4

## ARCI Matrix
Decision/Activity | Authority | Criteria | Escalation
Release Go/No-Go | Product Owner + Test Manager | All P1/Critical defects resolved, >95% test pass rate, compliance gates passed | VP of Product for tie-breaking
Quality Gate Approval | Test Manager + QA Lead | Gate-specific entry/exit criteria met | Product Owner if criteria cannot be met
Defect Priority/Severity Assignment | QA Lead | Business impact and technical severity assessment | Test Manager if Product Owner disputes priority
Test Scope Changes | Test Manager + QA Lead | Risk impact analysis and schedule feasibility | Product Owner for business-critical changes
Environment Reset/Refresh | DevOps Engineer + QA Lead | Technical necessity and impact to test schedule | Test Manager if impacts release timeline
Test Automation Investment | QA Lead + Automation Engineers | ROI analysis, maintenance burden assessment | Test Manager for cross-project prioritization
Security Test Scope | Security Tester + QA Lead | Compliance requirements and threat modeling | Dev Lead for feasibility, Test Manager for scheduling
Performance Test Baseline Acceptance | Performance Engineer + Product Owner | SLA achievement, business requirements met | Dev Lead if performance optimization required

## Quality Gates
Gate | Stage | Timing | Criteria | Approver
G1 - Requirements Review and Approval | Planning Phase | Week 1-2 of project | All 153 requirements documented in tool (JIRA/Azure DevOps), 25 features prioritized with business value assessment, 103 NFRs mapped to test design techniques, RTM baseline created with 100% requirement coverage planned, Compliance requirements identified (PCI DSS, GDPR, WCAG, OWASP), Acceptance criteria defined for all user stories | Product Owner + QA Lead
G2 - Test Strategy and Design Approval | Design Phase | Week 3-4 | Test strategy approved (6 test levels defined), Risk assessment completed with Class A/B/C classification, Test design techniques selected per requirement complexity, Test architecture and automation framework design reviewed, Test environment setup requirements documented, Resource allocation and schedule finalized | Test Manager + QA Lead + Dev Lead
G3 - Test Readiness Review | Pre-Execution Phase | Week before testing starts | Test environments deployed and verified (99.9% stability), Test data prepared and anonymized per GDPR, Automation framework implemented and validated, Test cases designed and reviewed (minimum 80% complete), Tools configured and accessible to team, Entry/exit criteria for each test level documented | QA Lead + DevOps Engineer
G4 - Test Completion and Quality Achievement | Execution Phase | Daily check, final approval before release | 95%+ of planned test cases executed, 95%+ test pass rate on critical/high priority tests, All P1/Critical defects fixed and re-tested, 95%+ of P2/High defects resolved or accepted, Coverage metrics achieved (code 80%, requirement 100%), RTM 100% complete and traced | Test Manager + QA Lead
G5 - Security, Compliance, and Performance Validation | Pre-Release Phase | Final week before release | SAST testing complete with zero Critical findings, DAST/penetration testing complete with zero Critical/High findings, PCI DSS compliance validation passed, GDPR data protection controls validated, WCAG 2.1 AA accessibility compliance confirmed, Performance testing passed (p95 <2s, load test success), Dependency vulnerability scan clean | Security Tester + Performance Engineer + QA Lead
G6 - Release Approval and Go/No-Go Decision | Release Phase | Final sign-off before deployment | All quality gates G1-G5 passed, Risk register reviewed with all high risks mitigated/accepted, Release notes prepared and reviewed, Rollback procedures documented and tested, Deployment plan reviewed by DevOps, Stakeholder sign-off obtained (Product Owner, Test Manager, Dev Lead) | Product Owner + Test Manager + Dev Lead

## Exit Criteria
Gate | Exit Criteria | Entry Criteria
G1 - Requirements Review and Approval | RTM created, test strategy draft approved | Requirements document reviewed and signed by BA
G2 - Test Strategy and Design Approval | Test plans approved, resources allocated, environments provisioned | Test strategy draft and risk assessment available
G3 - Test Readiness Review | Team sign-off on readiness, testing can commence | All test cases designed, environments ready
G4 - Test Completion and Quality Achievement | >95% tests executed and passed, defect metrics acceptable | Testing underway, minimum 50% test execution complete
G5 - Security, Compliance, and Performance Validation | All compliance and security gates passed, no critical findings | All security/performance tests planned and scheduled
G6 - Release Approval and Go/No-Go Decision | Go decision documented, deployment authorized | All quality validation complete, no open critical defects

## Coverage Dashboard
KPI | Target Value | Description
G1 - Requirements Review and Approval | Week 1-2 of project | All 153 requirements documented in tool (JIRA/Azure DevOps), 25 features prioritized with business value assessment, 103 NFRs mapped to test design techniques, RTM baseline created with 100% requirement coverage planned, Compliance requirements identified (PCI DSS, GDPR, WCAG, OWASP), Acceptance criteria defined for all user stories
G2 - Test Strategy and Design Approval | Week 3-4 | Test strategy approved (6 test levels defined), Risk assessment completed with Class A/B/C classification, Test design techniques selected per requirement complexity, Test architecture and automation framework design reviewed, Test environment setup requirements documented, Resource allocation and schedule finalized
G3 - Test Readiness Review | Week before testing starts | Test environments deployed and verified (99.9% stability), Test data prepared and anonymized per GDPR, Automation framework implemented and validated, Test cases designed and reviewed (minimum 80% complete), Tools configured and accessible to team, Entry/exit criteria for each test level documented
G4 - Test Completion and Quality Achievement | Daily check, final approval before release | 95%+ of planned test cases executed, 95%+ test pass rate on critical/high priority tests, All P1/Critical defects fixed and re-tested, 95%+ of P2/High defects resolved or accepted, Coverage metrics achieved (code 80%, requirement 100%), RTM 100% complete and traced
G5 - Security, Compliance, and Performance Validation | Final week before release | SAST testing complete with zero Critical findings, DAST/penetration testing complete with zero Critical/High findings, PCI DSS compliance validation passed, GDPR data protection controls validated, WCAG 2.1 AA accessibility compliance confirmed, Performance testing passed (p95 <2s, load test success), Dependency vulnerability scan clean
G6 - Release Approval and Go/No-Go Decision | Final sign-off before deployment | All quality gates G1-G5 passed, Risk register reviewed with all high risks mitigated/accepted, Release notes prepared and reviewed, Rollback procedures documented and tested, Deployment plan reviewed by DevOps, Stakeholder sign-off obtained (Product Owner, Test Manager, Dev Lead)